## Slide 1: Mid Day Meal Scheme
Ministry of HRD
Government of India
PAB-MDM Meeting
Dadra & Nagar Haveli
on
02.02.2017

## Slide 2: Review of Implementation of MDMS in Dadra & Nagar Haveli (Primary + Upper Primary) (1.4.2016 to 31.12.2016)
Part-I
Ministry of HRD, Govt. of India

## Slide 3: Best Practices
UT is providing additional cooking cost of Rs 9.37 in primary and Rs. 10.11 in upper primary.
UT is providing Rs. 2831 additional Honorarium to to the Cook cum helper. (Rs.3831/month)
Seasonal fruits, Sukhadi, Lapsi (sweet dalia), Sheera are served.
LPG (100%) in all schools.
Toll free No. 1800-233-0260 in which the any complaints related with MDMS

## Slide 4: Issues
Ministry of HRD, Govt. of India
Almost 2.3 months delay in the fund release from U.T Administration to the District Authority.
Only one meeting of District Level Committee held under the Chairmanship of Member of Parliament (Lok Sabha).

## Slide 5: Coverage : CHILDREN Enrolment vs Achievement (PRY)
No. of Children (in Thousands)
78%
80%
Ministry of HRD, Govt. of India
79%

## Slide 6: Coverage : CHILDREN Enrolment vs Achievement (U.PRY)
No. of Children (in Thousands)
77%
78%
Ministry of HRD, Govt. of India
77%

## Slide 7: Payment of cost of food grains to FCI (Rs in Lakh)
100%

## Slide 8: FOOD GRAIN : ALLOCATION vs. UTILISATION
Ministry of HRD, Govt. of India
Quantity in MTs
61%
62%
52%

## Slide 9: COOKING COST: ALLOCATION vs UTILISATION
Ministry of HRD, Govt. of India
Rs in Lakhs
67%
54%
62%

## Slide 10: Honorarium to Cooks-cum-Helpers
Rs. In Lakh
Ministry of HRD, Govt. of India
77%

## Slide 11: Transportation Assistance : ALLOCATION vs UTILISATION
Ministry of HRD, Govt. of India
Rs in Lakhs
14%
27%
86%

## Slide 12: MME: ALLOCATION vs UTILISATION
Ministry of HRD, Govt. of India
Rs in Lakhs

## Slide 13: Achievement up to 2016-17 Kitchen cum Stores
Progress (in %)
Ministry of HRD, Govt. of India
Total Sanctioned : 50 Kitchen Cum Stores
50 KS

## Slide 14: Coverage : School Health Programme
Ministry of HRD, Govt. of India
Details | Institutions | Children
Total | 283 | 42020
Health Check UP | 271 | 39972 (95%)
IFA Distribution | 271 | 40704 (97%)
Deworming Tablets | 271 | 40704 (97%)
Spectacles | 271 | 76

## Slide 15: Summary of performance - Physical
Percentage

## Slide 16: Summary of performance – Financial
Percentage

## Slide 17: Automated Monitoring System
Month(2017) | Meals Served | Days
January | 46650 | 9
ASM stated in UT on 20th January, 2017

## Slide 18
Comparison of data: MIS vs AWP&B
Chart: 
| Institutions | Working Days | Coverage of children | CCH engaged | CCH Hon. (Rs. in Lakhs) | Cooking Cost (Rs. in Lakhs) | Food Grains (in MTs) | Drinking water | Toilet Facility | LPG
MIS | 100 | 100 | 78.2889 | 99.7843 | 67.3662 | 64.9596 | 30.3617 | 98.5866 | 95.4064 | 97.5265
AWPB | 100 | 100.6211 | 77.5202 | 99.7843 | 77.4829 | 67.5249 | 61.5035 | 100 | 100 | 100

## Slide 19: Score Card all components : 3 years
2014-15
2015-16
2016-17

## Slide 20: Analysis of UT’s Proposal for 2017-18
Ministry of HRD, Govt. of India
Part-II

## Slide 21: Proposal for 2017-18 : Children (PRIMARY)
No. of children (in Thousand)
Ministry of HRD, Govt. of India
Q-1
Q-2
Q-3
Average
Proposal
Recommend

## Slide 22: Proposal for 2017-18 : Children (Up. PRIMARY)
No. of children (in Thousand)
Ministry of HRD, Govt. of India
Q-1
Q-2
Q-3
Average
Proposal
Recommend

## Slide 23: Proposals and Recommendations
Ministry of HRD, Govt. of India
S. No | Component | PAB Approval 2016-17 | Proposal for AWP&B 17-18 | Recommendation by Appraisal Team
1 | Children (Pry) | 20200 | 19400 | 19400
2 | Children (U Pry) | 14500 | 13900 | 13900
3 | Working Day (Pry and U Pry) | 231 – Pry & U Pry | 231 – Pry & U Pry | 231 – Pry & U Pry
4 | Kitchen cum Store | Nil | 100 | Not recommended
5 | Cook cum Helper | 925 | 925 (no additional) | 925 (no additional)
6 | Kitchen Devices | Nil | Nil | Nil
7 | Kitchen Devices (Replacement/Repair) | Nil | Nil | Nil
8 | MME Plan | Rs 30 lakh | Rs 30 lakh | Rs 30 lakh
9 | Notional Requirement of Central Assistance | Rs. 549.63 Lakh |  | Rs. 538.44 Lakh

## Slide 24
Ministry of HRD, Govt. of India
Thank you