## Odisha revised
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2018-19
State : Odisha
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2017-18
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2017-18 | Average number of children availed MDM during 2017-18 | Diff | Diff in %
Primary | 2961774 | 2654750 | -307024 | -10.37%
Up Primary | 1657912 | 1618403 | -39509 | -2.383%
NCLP | 0 | 0 | 0 | #DIV/0!
Total | 4619686 | 4273153 | -346533 | -7.501%
1.2) No. of School working days
PY | 239 | 232 | -7 | -2.929%
UP.PY | 239 | 232 | -7 | -2.929%
NCLP | 0 |  | 0 | #DIV/0!
1.3) Number of meals served vis-à-vis PAB approval during 2017-18
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 707863986 | 603805660 | -104058326 | -14.7%
UP PY | 396240968 | 368151771 | -28089197 | -7.089%
NCLP | 0 |  | 0 | #DIV/0!
Total | 1104104954 | 971957431 | -132147523 | -11.97%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | ANGUL | 902 | 902 | 0 | 0%
2 | BALASORE | 1517 | 1517 | 0 | 0%
3 | BARAGARH | 944 | 944 | 0 | 0%
4 | BHADRAK | 1087 | 1087 | 0 | 0%
5 | BOLANGIR | 1290 | 1290 | 0 | 0%
6 | BOUDH | 494 | 494 | 0 | 0%
7 | CUTTACK | 1364 | 1364 | 0 | 0%
8 | DEOGARH | 343 | 343 | 0 | 0%
9 | DHENKANAL | 816 | 816 | 0 | 0%
10 | GAJAPATI | 852 | 852 | 0 | 0%
11 | GANJAM | 2186 | 2186 | 0 | 0%
12 | JAGATSINGHPUR | 896 | 896 | 0 | 0%
13 | JAJPUR | 1280 | 1280 | 0 | 0%
14 | JHARSUGUDA | 368 | 368 | 0 | 0%
15 | KALAHANDI | 1566 | 1566 | 0 | 0%
16 | KANDHAMAL | 1101 | 1101 | 0 | 0%
17 | KENDRAPARA | 1130 | 1130 | 0 | 0%
18 | KEONJHAR | 1659 | 1659 | 0 | 0%
19 | KHURDHA | 881 | 881 | 0 | 0%
20 | KORAPUT | 1698 | 1698 | 0 | 0%
21 | MALKANGIRI | 872 | 872 | 0 | 0%
22 | MAYURBHANJ | 2761 | 2761 | 0 | 0%
23 | NAWARANGPUR | 1190 | 1190 | 0 | 0%
24 | NAYAGARH | 696 | 696 | 0 | 0%
25 | NUAPADA | 534 | 534 | 0 | 0%
26 | PURI | 1218 | 1218 | 0 | 0%
27 | RAYAGADA | 1293 | 1293 | 0 | 0%
28 | SAMBALPUR | 852 | 852 | 0 | 0%
29 | SONEPUR | 552 | 552 | 0 | 0%
30 | SUNDERGARH | 1594 | 1594 | 0 | 0%
| TOTAL | 33936 | 33936 | 0 | 0%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | ANGUL | 536 | 536 | 0 | 0
2 | BALASORE | 675 | 675 | 0 | 0
3 | BARAGARH | 620 | 620 | 0 | 0
4 | BHADRAK | 550 | 550 | 0 | 0
5 | BOLANGIR | 841 | 841 | 0 | 0
6 | BOUDH | 274 | 274 | 0 | 0
7 | CUTTACK | 686 | 686 | 0 | 0
8 | DEOGARH | 197 | 197 | 0 | 0
9 | DHENKANAL | 528 | 528 | 0 | 0
10 | GAJAPATI | 511 | 511 | 0 | 0
11 | GANJAM | 1083 | 1083 | 0 | 0
12 | JAGATSINGHPUR | 365 | 365 | 0 | 0
13 | JAJPUR | 787 | 787 | 0 | 0
14 | JHARSUGUDA | 236 | 236 | 0 | 0
15 | KALAHANDI | 723 | 723 | 0 | 0
16 | KANDHAMAL | 755 | 755 | 0 | 0
17 | KENDRAPARA | 531 | 531 | 0 | 0
18 | KEONJHAR | 713 | 713 | 0
19 | KHURDHA | 441 | 441 | 0
20 | KORAPUT | 873 | 873 | 0
21 | MALKANGIRI | 460 | 460 | 0
22 | MAYURBHANJ | 1161 | 1161 | 0
23 | NAWARANGPUR | 680 | 680 | 0
24 | NAYAGARH | 361 | 361 | 0
25 | NUAPADA | 426 | 426 | 0
26 | PURI | 566 | 566 | 0
27 | RAYAGADA | 677 | 677 | 0
28 | SAMBALPUR | 441 | 441 | 0
29 | SONEPUR | 313 | 313 | 0
30 | SUNDERGARH | 795 | 795 | 0
| TOTAL | 17805 | 17805 | 0 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2018-19)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | ANGUL | 222 | 222 | 0 | 0%
2 | BALASORE | 715 | 715 | 0 | 0%
3 | BARAGARH | 260 | 260 | 0 | 0%
4 | BHADRAK | 290 | 290 | 0 | 0%
5 | BOLANGIR | 296 | 296 | 0 | 0%
6 | BOUDH | 39 | 39 | 0 | 0%
7 | CUTTACK | 354 | 354 | 0 | 0%
8 | DEOGARH | 58 | 58 | 0 | 0%
9 | DHENKANAL | 213 | 213 | 0 | 0%
10 | GAJAPATI | 53 | 53 | 0 | 0%
11 | GANJAM | 325 | 325 | 0 | 0%
12 | JAGATSINGHPUR | 271 | 271 | 0 | 0%
13 | JAJPUR | 477 | 477 | 0 | 0%
14 | JHARSUGUDA | 86 | 86 | 0 | 0%
15 | KALAHANDI | 181 | 181 | 0 | 0%
16 | KANDHAMAL | 95 | 95 | 0 | 0%
17 | KENDRAPARA | 370 | 370 | 0 | 0%
18 | KEONJHAR | 547 | 547 | 0 | 0%
19 | KHURDHA | 258 | 258 | 0 | 0%
20 | KORAPUT | 125 | 125 | 0 | 0%
21 | MALKANGIRI | 66 | 66 | 0 | 0%
22 | MAYURBHANJ | 545 | 545 | 0 | 0%
23 | NAWARANGPUR | 85 | 85 | 0 | 0%
24 | NAYAGARH | 149 | 149 | 0 | 0%
25 | NUAPADA | 66 | 66 | 0 | 0%
26 | PURI | 384 | 384 | 0 | 0%
27 | RAYAGADA | 65 | 65 | 0 | 0%
28 | SAMBALPUR | 116 | 116 | 0 | 0%
29 | SONEPUR | 68 | 68 | 0 | 0%
30 | SUNDERGARH | 264 | 264 | 0 | 0%
| TOTAL | 7043 | 7043 | 0 | 0%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2018-19)
Sl. No. | Districts | Enrolment as on 30.9.2017 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ANGUL | 80820 | 75295 | -5525 | -6.836%
2 | BALASORE | 171308 | 161385 | -9923 | -5.792%
3 | BARAGARH | 90231 | 79092 | -11139 | -12.34%
4 | BHADRAK | 110900 | 92063 | -18837 | -16.99%
5 | BOLANGIR | 131219 | 102974 | -28245 | -21.53%
6 | BOUDH | 35656 | 30293 | -5363 | -15.04%
7 | CUTTACK | 111239 | 95452 | -15787 | -14.19%
8 | DEOGARH | 20581 | 19973 | -608 | -2.954%
9 | DHENKANAL | 75054 | 67739 | -7315 | -9.746%
10 | GAJAPATI | 52341 | 47957 | -4384 | -8.376%
11 | GANJAM | 209112 | 183362 | -25750 | -12.31%
12 | JAGATSINGHPUR | 49175 | 48608 | -567 | -1.153%
13 | JAJPUR | 112941 | 110700 | -2241 | -1.984%
14 | JHARSUGUDA | 28536 | 23775 | -4761 | -16.68%
15 | KALAHANDI | 130175 | 119996 | -10179 | -7.819%
16 | KANDHAMAL | 81944 | 70568 | -11376 | -13.88%
17 | KENDRAPARA | 90949 | 84515 | -6434 | -7.074%
18 | KEONJHAR | 150155 | 136582 | -13573 | -9.039%
19 | KHURDHA | 85329 | 81145 | -4184 | -4.903%
20 | KORAPUT | 145151 | 126345 | -18806 | -12.96%
21 | MALKANGIRI | 81280 | 77445 | -3835 | -4.718%
22 | MAYURBHANJ | 220614 | 220089 | -525 | -0.238%
23 | NAWARANGPUR | 139083 | 118103 | -20980 | -15.08%
24 | NAYAGARH | 56570 | 48457 | -8113 | -14.34%
25 | NUAPADA | 55250 | 49418 | -5832 | -10.56%
26 | PURI | 87810 | 80674 | -7136 | -8.127%
27 | RAYAGADA | 104522 | 93380 | -11142 | -10.66%
28 | SAMBALPUR | 61276 | 52836 | -8440 | -13.77%
29 | SONEPUR | 40575 | 35683 | -4892 | -12.06%
30 | SUNDERGARH | 136192 | 120846 | -15346 | -11.27%
| TOTAL | 2945988 | 2654750 | -291238 | -9.886%
2.4 Coverage Chidlren vs. Enrolment ( Up Pry) (Source data : Table AT- 4A & 5-A of AWP&B 2018-19)
Sl. No. | Districts | Enrolment as on 30.9.2017 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ANGUL | 53033 | 47127 | -5906 | -11.14%
2 | BALASORE | 115266 | 103543 | -11723 | -10.17%
3 | BARAGARH | 61341 | 55427 | -5914 | -9.641%
4 | BHADRAK | 73839 | 64765 | -9074 | -12.29%
5 | BOLANGIR | 88420 | 65328 | -23092 | -26.12%
6 | BOUDH | 24898 | 20018 | -4880 | -19.6%
7 | CUTTACK | 81887 | 68734 | -13153 | -16.06%
8 | DEOGARH | 15241 | 14700 | -541 | -3.55%
9 | DHENKANAL | 50975 | 43213 | -7762 | -15.23%
10 | GAJAPATI | 29264 | 21528 | -7736 | -26.44%
11 | GANJAM | 151850 | 135366 | -16484 | -10.86%
12 | JAGATSINGHPUR | 36391 | 34044 | -2347 | -6.449%
13 | JAJPUR | 90396 | 66977 | -23419 | -25.91%
14 | JHARSUGUDA | 20135 | 16199 | -3936 | -19.55%
15 | KALAHANDI | 87580 | 72537 | -15043 | -17.18%
16 | KANDHAMAL | 44466 | 36655 | -7811 | -17.57%
17 | KENDRAPARA | 61415 | 54108 | -7307 | -11.9%
18 | KEONJHAR | 85692 | 74270 | -11422 | -13.33%
19 | KHURDHA | 65485 | 56591 | -8894 | -13.58%
20 | KORAPUT | 64020 | 47816 | -16204 | -25.31%
21 | MALKANGIRI | 31714 | 25509 | -6205 | -19.57%
22 | MAYURBHANJ | 144122 | 131298 | -12824 | -8.898%
23 | NAWARANGPUR | 74715 | 61939 | -12776 | -17.1%
24 | NAYAGARH | 40110 | 34012 | -6098 | -15.2%
25 | NUAPADA | 39841 | 35254 | -4587 | -11.51%
26 | PURI | 65707 | 60860 | -4847 | -7.377%
27 | RAYAGADA | 45709 | 35710 | -9999 | -21.88%
28 | SAMBALPUR | 40746 | 36240 | -4506 | -11.06%
29 | SONEPUR | 27584 | 23594 | -3990 | -14.46%
30 | SUNDERGARH | 83827 | 75041 | -8786 | -10.48%
| TOTAL | 1895669 | 1618403 | -277266 | -14.63%
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ANGUL | 77099 | 75295 | -1804 | -2.34%
2 | BALASORE | 180066 | 161385 | -18681 | -10.37%
3 | BARAGARH | 88753 | 79092 | -9661 | -10.89%
4 | BHADRAK | 114772 | 92063 | -22709 | -19.79%
5 | BOLANGIR | 115957 | 102974 | -12983 | -11.2%
6 | BOUDH | 35058 | 30293 | -4765 | -13.59%
7 | CUTTACK | 106492 | 95452 | -11040 | -10.37%
8 | DEOGARH | 21958 | 19973 | -1985 | -9.04%
9 | DHENKANAL | 69914 | 67739 | -2175 | -3.111%
10 | GAJAPATI | 58884 | 47957 | -10927 | -18.56%
11 | GANJAM | 208596 | 183362 | -25234 | -12.1%
12 | JAGATSINGHPUR | 53988 | 48608 | -5380 | -9.965%
13 | JAJPUR | 124377 | 110700 | -13677 | -11%
14 | JHARSUGUDA | 25548 | 23775 | -1773 | -6.94%
15 | KALAHANDI | 136440 | 119996 | -16444 | -12.05%
16 | KANDHAMAL | 87095 | 70568 | -16527 | -18.98%
17 | KENDRAPARA | 91707 | 84515 | -7192 | -7.842%
18 | KEONJHAR | 159031 | 136582 | -22449 | -14.12%
19 | KHURDHA | 92170 | 81145 | -11025 | -11.96%
20 | KORAPUT | 133037 | 126345 | -6692 | -5.03%
21 | MALKANGIRI | 78078 | 77445 | -633 | -0.8107%
22 | MAYURBHANJ | 236702 | 220089 | -16613 | -7.019%
23 | NAWARANGPUR | 138500 | 118103 | -20397 | -14.73%
24 | NAYAGARH | 55667 | 48457 | -7210 | -12.95%
25 | NUAPADA | 56608 | 49418 | -7190 | -12.7%
26 | PURI | 80165 | 80674 | 509 | 0.6349%
27 | RAYAGADA | 93014 | 93380 | 366 | 0.3935%
28 | SAMBALPUR | 62994 | 52836 | -10158 | -16.13%
29 | SONEPUR | 35764 | 35683 | -81 | -0.2265%
30 | SUNDERGARH | 143340 | 120846 | -22494 | -15.69%
| TOTAL | 2961774 | 2654750 | -307024 | -10.37%
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2018-19)
Sl. No. | Districts | No. of children as per PAB Approval for 2017-18 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | ANGUL | 47535 | 47127 | -408 | -0.8583%
2 | BALASORE | 107510 | 103543 | -3967 | -3.69%
3 | BARAGARH | 53464 | 55427 | 1963 | 3.672%
4 | BHADRAK | 64959 | 64765 | -194 | -0.2986%
5 | BOLANGIR | 71001 | 65328 | -5673 | -7.99%
6 | BOUDH | 21671 | 20018 | -1653 | -7.628%
7 | CUTTACK | 73031 | 68734 | -4297 | -5.884%
8 | DEOGARH | 15198 | 14700 | -498 | -3.277%
9 | DHENKANAL | 44646 | 43213 | -1433 | -3.21%
10 | GAJAPATI | 25500 | 21528 | -3972 | -15.58%
11 | GANJAM | 134843 | 135366 | 523 | 0.3879%
12 | JAGATSINGHPUR | 36782 | 34044 | -2738 | -7.444%
13 | JAJPUR | 68775 | 66977 | -1798 | -2.614%
14 | JHARSUGUDA | 17241 | 16199 | -1042 | -6.044%
15 | KALAHANDI | 74429 | 72537 | -1892 | -2.542%
16 | KANDHAMAL | 36997 | 36655 | -342 | -0.9244%
17 | KENDRAPARA | 54394 | 54108 | -286 | -0.5258%
18 | KEONJHAR | 77222 | 74270 | -2952 | -3.823%
19 | KHURDHA | 55790 | 56591 | 801 | 1.436%
20 | KORAPUT | 50057 | 47816 | -2241 | -4.477%
21 | MALKANGIRI | 25509 | 25509 | 0 | 0%
22 | MAYURBHANJ | 131326 | 131298 | -28 | -0.02132%
23 | NAWARANGPUR | 59023 | 61939 | 2916 | 4.94%
24 | NAYAGARH | 39252 | 34012 | -5240 | -13.35%
25 | NUAPADA | 35232 | 35254 | 22 | 0.06244%
26 | PURI | 64614 | 60860 | -3754 | -5.81%
27 | RAYAGADA | 37183 | 35710 | -1473 | -3.961%
28 | SAMBALPUR | 35568 | 36240 | 672 | 1.889%
29 | SONEPUR | 22504 | 23594 | 1090 | 4.844%
30 | SUNDERGARH | 76656 | 75041 | -1615 | -2.107%
| TOTAL | 1657912 | 1618403 | -39509 | -2.383%
2.7 Number of meal to be served and actual number of meal served during 2017-18 (Source data: Table AT-5 & 5A of AWP&B 2018-19)
Sr. No. | District | No of meals to be served during 2017-18 | No of meal served during 2017-18 | % Meals Served
1 | 2 | 3 | 4 | 5
1 | ANGUL | 29787526 | 28034537 | 94.12%
2 | BALASORE | 68730664 | 61463361 | 89.43%
3 | BARAGARH | 33989863 | 30266702 | 89.05%
4 | BHADRAK | 42955709 | 36383963 | 84.7%
5 | BOLANGIR | 44682962 | 37026411 | 82.86%
6 | BOUDH | 13558231 | 11018200 | 81.27%
7 | CUTTACK | 42905997 | 37270373 | 86.87%
8 | DEOGARH | 8880284 | 7940229 | 89.41%
9 | DHENKANAL | 27379840 | 25408032 | 92.8%
10 | GAJAPATI | 20167776 | 16120491 | 79.93%
11 | GANJAM | 82081921 | 71395008 | 86.98%
12 | JAGATSINGHPUR | 21694030 | 18927226 | 87.25%
13 | JAJPUR | 46163328 | 41221096 | 89.29%
14 | JHARSUGUDA | 10226571 | 8874302 | 86.78%
15 | KALAHANDI | 50397691 | 43512387 | 86.34%
16 | KANDHAMAL | 29657988 | 23910718 | 80.62%
17 | KENDRAPARA | 34918139 | 31190228 | 89.32%
18 | KEONJHAR | 56464467 | 48706806 | 86.26%
19 | KHURDHA | 35362440 | 31266005 | 88.42%
20 | KORAPUT | 43759466 | 40231171 | 91.94%
21 | MALKANGIRI | 24757293 | 22855882 | 92.32%
22 | MAYURBHANJ | 87958692 | 81521807 | 92.68%
23 | NAWARANGPUR | 47207997 | 41049711 | 86.95%
24 | NAYAGARH | 22685641 | 18803020 | 82.89%
25 | NUAPADA | 21949760 | 18797229 | 85.64%
26 | PURI | 34602181 | 32835955 | 94.9%
27 | RAYAGADA | 31117083 | 28270868 | 90.85%
28 | SAMBALPUR | 23556318 | 19774817 | 83.95%
29 | SONEPUR | 13926052 | 13218687 | 94.92%
30 | SUNDERGARH | 52579044 | 44662209 | 84.94%
| TOTAL | 1104104954 | 971957431 | 88.03%
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2017 | 8997.97 | 9647.26 | 649.29 | 0%
2 | Allocation for 2017-18 | 130222.55 | 130222.5438 | -0.0062 | -4.761e-06%
3 | Lifting during 2017-18 |  |  | 0 | #DIV/0!
3.2) District-wise opening balance as on 1.4.2017 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
S.No. | Name of District | Allocation | Opening Stock as on 01.04.2017 | % of OS on allocation
1 | 2 | 3 | 4 | 5
1 | ANGUL | 3546.7958 | 136.01 | 3.835%
2 | BALASORE | 8157.8109 | 665.09 | 8.153%
3 | BARAGARH | 4037.8811 | 488.94 | 12.11%
4 | BHADRAK | 5071.8309 | 336.45 | 6.634%
5 | BOLANGIR | 5316.7581 | 244.38 | 4.596%
6 | BOUDH | 1614.7915 | 198.9 | 12.32%
7 | CUTTACK | 5163.3201 | 193.96 | 3.756%
8 | DEOGARH | 1069.6445 | 131.86 | 12.33%
9 | DHENKANAL | 3271.5037 | 428.7 | 13.1%
10 | GAJAPATI | 2321.5026 | 125.76 | 5.417%
11 | GANJAM | 9819.566 | 957.34 | 9.749%
12 | JAGATSINGHPUR | 2608.9479 | 131.28 | 5.032%
13 | JAJPUR | 5438.1941 | 349.95 | 6.435%
14 | JHARSUGUDA | 1228.687 | 173.38 | 14.11%
15 | KALAHANDI | 5929.1956 | 208.37 | 3.514%
16 | KANDHAMAL | 3407.9129 | 387.36 | 11.37%
17 | KENDRAPARA | 4141.8222 | 715.51 | 17.28%
18 | KEONJHAR | 6569.2496 | 190.39 | 2.898%
19 | KHURDHA | 4202.9345 | 694.85 | 16.53%
20 | KORAPUT | 4974.1277 | 78.1 | 1.57%
21 | MALKANGIRI | 2780.5619 | 47.32 | 1.702%
22 | MAYURBHANJ | 10365.2149 | 349.36 | 3.371%
23 | NAWARANGPUR | 5426.1246 | 245.48 | 4.524%
24 | NAYAGARH | 2737.6255 | 63.19 | 2.308%
25 | NUAPADA | 2615.9984 | 206.73 | 7.903%
26 | PURI | 4232.3554 | 695.93 | 16.44%
27 | RAYAGADA | 3556.0451 | 81.5 | 2.292%
28 | SAMBALPUR | 2780.6694 | 526.72 | 18.94%
29 | SONEPUR | 1661.528 | 250 | 15.05%
30 | SUNDERGARH | 6173.9436 | 344.45 | 5.579%
| TOTAL | 130222.5438 | 9647.26 | 7.408%
3.3) District-wise unspent balance as on 31.03.2018 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2018 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | ANGUL | 3546.7958 | 172.984 | 4.877%
2 | BALASORE | 8157.8109 | 842.9453 | 10.33%
3 | BARAGARH | 4037.8811 | 368.9994 | 9.138%
4 | BHADRAK | 5071.8309 | 10.9964 | 0.2168%
5 | BOLANGIR | 5316.7581 | 620.0354 | 11.66%
6 | BOUDH | 1614.7915 | 216.4888 | 13.41%
7 | CUTTACK | 5163.3201 | 445.6381 | 8.631%
8 | DEOGARH | 1069.6445 | 0.94855 | 0.08868%
9 | DHENKANAL | 3271.5037 | 210.7424 | 6.442%
10 | GAJAPATI | 2321.5026 | 143.0482 | 6.162%
11 | GANJAM | 9819.566 | 475.6037 | 4.843%
12 | JAGATSINGHPUR | 2608.9479 | 214.398 | 8.218%
13 | JAJPUR | 5438.1941 | 459.5161 | 8.45%
14 | JHARSUGUDA | 1228.687 | 160.8849 | 13.09%
15 | KALAHANDI | 5929.1956 | 553.9776 | 9.343%
16 | KANDHAMAL | 3407.9129 | 837.7925 | 24.58%
17 | KENDRAPARA | 4141.8222 | 961.7483 | 23.22%
18 | KEONJHAR | 6569.2496 | 733.8493 | 11.17%
19 | KHURDHA | 4202.9345 | 376.8848 | 8.967%
20 | KORAPUT | 4974.1277 | 104.0098 | 2.091%
21 | MALKANGIRI | 2780.5619 | 26.6219 | 0.9574%
22 | MAYURBHANJ | 10365.2149 | 526.636 | 5.081%
23 | NAWARANGPUR | 5426.1246 | 441.4831 | 8.136%
24 | NAYAGARH | 2737.6255 | 24.1994 | 0.884%
25 | NUAPADA | 2615.9984 | 255.2709 | 9.758%
26 | PURI | 4232.3554 | 4.2342 | 0.1%
27 | RAYAGADA | 3556.0451 | 11.1961 | 0.3148%
28 | SAMBALPUR | 2780.6694 | 867.3518 | 31.19%
29 | SONEPUR | 1661.528 | 244.0173 | 14.69%
30 | SUNDERGARH | 6173.9436 | 377.8208 | 6.12%
| TOTAL | 130222.5438 | 10690.3229 | 8.209%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Opening balance as on 01.4.17 | Lifting upto 31.03.18 | Total Availibility | % Availibility
130222.5438 | 9647.26 | 116646.3946 | 126293.6546 | 96.98%
Source: Table AT-6 & 6A of AWP&B 2018-19
3.5) District-wise Foodgrains availability as on 31.03.18 (Source data: Table AT-6 & 6A of AWP&B 2018-19)
(in MTs)
Sl. No. | District | Allocation | OB as on 01.04.2017 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ANGUL | 3546.7958 | 136.01 | 3380.03 | 3516.04 | 99.13%
2 | BALASORE | 8157.8109 | 665.09 | 7525.29 | 8190.38 | 100.4%
3 | BARAGARH | 4037.8811 | 488.94 | 3530.278 | 4019.218 | 99.54%
4 | BHADRAK | 5071.8309 | 336.45 | 4064.212 | 4400.662 | 86.77%
5 | BOLANGIR | 5316.7581 | 244.38 | 4796.9 | 5041.28 | 94.82%
6 | BOUDH | 1614.7915 | 198.9 | 1338.61 | 1537.51 | 95.21%
7 | CUTTACK | 5163.3201 | 193.96 | 4758.85 | 4952.81 | 95.92%
8 | DEOGARH | 1069.6445 | 131.86 | 831.43 | 963.29 | 90.06%
9 | DHENKANAL | 3271.5037 | 428.7 | 2817.63 | 3246.33 | 99.23%
10 | GAJAPATI | 2321.5026 | 125.76 | 1879.0576 | 2004.8176 | 86.36%
11 | GANJAM | 9819.566 | 957.34 | 8173.86 | 9131.2 | 92.99%
12 | JAGATSINGHPUR | 2608.9479 | 131.28 | 2365.64 | 2496.92 | 95.71%
13 | JAJPUR | 5438.1941 | 349.95 | 5008.61 | 5358.56 | 98.54%
14 | JHARSUGUDA | 1228.687 | 173.38 | 1054.746 | 1228.126 | 99.95%
15 | KALAHANDI | 5929.1956 | 208.37 | 5516.51 | 5724.88 | 96.55%
16 | KANDHAMAL | 3407.9129 | 387.36 | 3250.21 | 3637.57 | 106.7%
17 | KENDRAPARA | 4141.8222 | 715.51 | 3973.98 | 4689.49 | 113.2%
18 | KEONJHAR | 6569.2496 | 190.39 | 6271.96 | 6462.35 | 98.37%
19 | KHURDHA | 4202.9345 | 694.85 | 3450.94 | 4145.79 | 98.64%
20 | KORAPUT | 4974.1277 | 78.1 | 4601.3 | 4679.4 | 94.07%
21 | MALKANGIRI | 2780.5619 | 47.32 | 2548.04 | 2595.36 | 93.34%
22 | MAYURBHANJ | 10365.2149 | 349.36 | 9852.51 | 10201.87 | 98.42%
23 | NAWARANGPUR | 5426.1246 | 245.48 | 5007.081 | 5252.561 | 96.8%
24 | NAYAGARH | 2737.6255 | 63.19 | 2229.05 | 2292.24 | 83.73%
25 | NUAPADA | 2615.9984 | 206.73 | 2319.58 | 2526.31 | 96.57%
26 | PURI | 4232.3554 | 695.93 | 3297.88 | 3993.81 | 94.36%
27 | RAYAGADA | 3556.0451 | 81.5 | 3147.81 | 3229.31 | 90.81%
28 | SAMBALPUR | 2780.6694 | 526.72 | 2720.38 | 3247.1 | 116.8%
29 | SONEPUR | 1661.528 | 250 | 1578.96 | 1828.96 | 110.1%
30 | SUNDERGARH | 6173.9436 | 344.45 | 5355.06 | 5699.51 | 92.32%
| TOTAL | 130222.5438 | 9647.26 | 116646.3946 | 126293.6546 | 96.98%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
130222.5438 | 126293.6546 | 96.98% | 115603.3316 | 88.77%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2018-19)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | ANGUL | 3546.7958 | 3343.056 | 94.26%
2 | BALASORE | 8157.8109 | 7347.4347 | 90.07%
3 | BARAGARH | 4037.8811 | 3650.2186 | 90.4%
4 | BHADRAK | 5071.8309 | 4389.6656 | 86.55%
5 | BOLANGIR | 5316.7581 | 4421.2446 | 83.16%
6 | BOUDH | 1614.7915 | 1321.0212 | 81.81%
7 | CUTTACK | 5163.3201 | 4507.1719 | 87.29%
8 | DEOGARH | 1069.6445 | 962.3415 | 89.97%
9 | DHENKANAL | 3271.5037 | 3035.5876 | 92.79%
10 | GAJAPATI | 2321.5026 | 1861.7694 | 80.2%
11 | GANJAM | 9819.566 | 8655.5963 | 88.15%
12 | JAGATSINGHPUR | 2608.9479 | 2282.522 | 87.49%
13 | JAJPUR | 5438.1941 | 4899.0439 | 90.09%
14 | JHARSUGUDA | 1228.687 | 1067.2411 | 86.86%
15 | KALAHANDI | 5929.1956 | 5170.9024 | 87.21%
16 | KANDHAMAL | 3407.9129 | 2799.7775 | 82.16%
17 | KENDRAPARA | 4141.8222 | 3727.7417 | 90%
18 | KEONJHAR | 6569.2496 | 5728.5008 | 87.2%
19 | KHURDHA | 4202.9345 | 3768.9052 | 89.67%
20 | KORAPUT | 4974.1277 | 4575.3903 | 91.98%
21 | MALKANGIRI | 2780.5619 | 2568.7381 | 92.38%
22 | MAYURBHANJ | 10365.2149 | 9675.234 | 93.34%
23 | NAWARANGPUR | 5426.1246 | 4811.0779 | 88.67%
24 | NAYAGARH | 2737.6255 | 2268.0406 | 82.85%
25 | NUAPADA | 2615.9984 | 2271.0391 | 86.81%
26 | PURI | 4232.3554 | 3989.5758 | 94.26%
27 | RAYAGADA | 3556.0451 | 3218.1139 | 90.5%
28 | SAMBALPUR | 2780.6694 | 2379.7482 | 85.58%
29 | SONEPUR | 1661.528 | 1584.9427 | 95.39%
30 | SUNDERGARH | 6173.9436 | 5321.6892 | 86.2%
| TOTAL | 130222.5438 | 115603.3316 | 88.77%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
3906.6763 | 3499.3918 | 3499.3918 | 100%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ANGUL | 106.4039 | 101.4009 | 101.4009 | 0 | 100%
2 | BALASORE | 244.7343 | 225.7587 | 225.7587 | 0 | 100%
3 | BARAGARH | 121.1364 | 105.9083 | 105.9083 | 0 | 100%
4 | BHADRAK | 152.1549 | 121.9264 | 121.9264 | 0 | 100%
5 | BOLANGIR | 159.5027 | 143.907 | 143.907 | 0 | 100%
6 | BOUDH | 48.4437 | 40.1583 | 40.1583 | 0 | 100%
7 | CUTTACK | 154.8996 | 142.7655 | 142.7655 | 0 | 100%
8 | DEOGARH | 32.0893 | 24.9429 | 24.9429 | 0 | 100%
9 | DHENKANAL | 98.1451 | 84.5289 | 84.5289 | 0 | 100%
10 | GAJAPATI | 69.6451 | 56.3717 | 56.3717 | 0 | 100%
11 | GANJAM | 294.587 | 245.2158 | 245.2158 | 0 | 100%
12 | JAGATSINGHPUR | 78.2684 | 70.9692 | 70.9692 | 0 | 100%
13 | JAJPUR | 163.1458 | 150.2583 | 150.2583 | 0 | 100%
14 | JHARSUGUDA | 36.8606 | 31.6424 | 31.6424 | 0 | 100%
15 | KALAHANDI | 177.8759 | 165.4953 | 165.4953 | 0 | 100%
16 | KANDHAMAL | 102.2374 | 97.5063 | 97.5063 | 0 | 100%
17 | KENDRAPARA | 124.2547 | 119.2194 | 119.2194 | 0 | 100%
18 | KEONJHAR | 197.0775 | 188.1588 | 188.1588 | 0 | 100%
19 | KHURDHA | 126.088 | 103.5282 | 103.5282 | 0 | 100%
20 | KORAPUT | 149.2238 | 138.039 | 138.039 | 0 | 100%
21 | MALKANGIRI | 83.4169 | 76.4412 | 76.4412 | 0 | 100%
22 | MAYURBHANJ | 310.9564 | 295.5753 | 295.5753 | 0 | 100%
23 | NAWARANGPUR | 162.7837 | 150.2124 | 150.2124 | 0 | 100%
24 | NAYAGARH | 82.1288 | 66.8715 | 66.8715 | 0 | 100%
25 | NUAPADA | 78.48 | 69.5874 | 69.5874 | 0 | 100%
26 | PURI | 126.9707 | 98.9364 | 98.9364 | 0 | 100%
27 | RAYAGADA | 106.6814 | 94.4343 | 94.4343 | 0 | 100%
28 | SAMBALPUR | 83.4201 | 81.6114 | 81.6114 | 0 | 100%
29 | SONEPUR | 49.8458 | 47.3688 | 47.3688 | 0 | 100%
30 | SUNDERGARH | 185.2183 | 160.6518 | 160.6518 | 0 | 100%
| TOTAL | 3906.6763 | 3499.3918 | 3499.3918 | 0 | 100%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 01.04.2017 (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2017 | % of OB on allocation
1 | 2 | 3 | 4 | 5
1 | ANGUL | 1619.8882 | 0.16856 | 0.01041%
2 | BALASORE | 3725.9994 | 0 | 0%
3 | BARAGARH | 1844.2384 | 404.7403 | 21.95%
4 | BHADRAK | 2316.6885 | 122.2927 | 5.279%
5 | BOLANGIR | 2428.2875 | 6.4507 | 0.2656%
6 | BOUDH | 737.5028 | 47.1184 | 6.389%
7 | CUTTACK | 2357.8189 | 1.2035 | 0.05105%
8 | DEOGARH | 488.4443 | 41.0263 | 8.399%
9 | DHENKANAL | 1494.0805 | 58.5976 | 3.922%
10 | GAJAPATI | 1060.8104 | 43.4079 | 4.092%
11 | GANJAM | 4484.4702 | 568.5186 | 12.68%
12 | JAGATSINGHPUR | 1191.3818 | 197.4903 | 16.58%
13 | JAJPUR | 2484.118 | 0.46314 | 0.01864%
14 | JHARSUGUDA | 561.0904 | 78.2297 | 13.94%
15 | KALAHANDI | 2708.4562 | 47.5345 | 1.755%
16 | KANDHAMAL | 1557.2872 | 93.7443 | 6.02%
17 | KENDRAPARA | 1891.7545 | 657.6526 | 34.76%
18 | KEONJHAR | 3001.3339 | 106.5355 | 3.55%
19 | KHURDHA | 1919.6105 | 29.7803 | 1.551%
20 | KORAPUT | 2273.3651 | 0 | 0%
21 | MALKANGIRI | 1271.0587 | 9.4659 | 0.7447%
22 | MAYURBHANJ | 4734.7137 | 103.3279 | 2.182%
23 | NAWARANGPUR | 2479.5224 | 186.0893 | 7.505%
24 | NAYAGARH | 1250.08 | 137.3395 | 10.99%
25 | NUAPADA | 1194.7591 | 7.3998 | 0.6194%
26 | PURI | 1932.2417 | 52.4351 | 2.714%
27 | RAYAGADA | 1625.114 | 42.5208 | 2.616%
28 | SAMBALPUR | 1270.1463 | 407.8959 | 32.11%
29 | SONEPUR | 758.8284 | 20.7644 | 2.736%
30 | SUNDERGARH | 2820.3379 | 0 | 0%
| TOTAL | 59483.4287 | 3472.1934 | 5.837%
4.1.2) District-wise unspent balance as on 31.03.2018 Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2018 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | ANGUL | 1619.8882 | 76.4298 | 4.718%
2 | BALASORE | 3725.9994 | 331.9772 | 8.91%
3 | BARAGARH | 1844.2384 | 145.1225 | 7.869%
4 | BHADRAK | 2316.6885 | 287.4245 | 12.41%
5 | BOLANGIR | 2428.2875 | 383.8974 | 15.81%
6 | BOUDH | 737.5028 | 125.0659 | 16.96%
7 | CUTTACK | 2357.8189 | 276.656 | 11.73%
8 | DEOGARH | 488.4443 | 42.4695 | 8.695%
9 | DHENKANAL | 1494.0805 | 90.3703 | 6.049%
10 | GAJAPATI | 1060.8104 | 196.8694 | 18.56%
11 | GANJAM | 4484.4702 | 467.2458 | 10.42%
12 | JAGATSINGHPUR | 1191.3818 | 130.2073 | 10.93%
13 | JAJPUR | 2484.118 | 220.5569 | 8.879%
14 | JHARSUGUDA | 561.0904 | 65.4248 | 11.66%
15 | KALAHANDI | 2708.4562 | 316.9162 | 11.7%
16 | KANDHAMAL | 1557.2872 | 258.1274 | 16.58%
17 | KENDRAPARA | 1891.7545 | 146.7515 | 7.757%
18 | KEONJHAR | 3001.3339 | 341.3855 | 11.37%
19 | KHURDHA | 1919.6105 | 177.8972 | 9.267%
20 | KORAPUT | 2273.3651 | 157 | 6.906%
21 | MALKANGIRI | 1271.0587 | 82.0339 | 6.454%
22 | MAYURBHANJ | 4734.7137 | 252.8064 | 5.339%
23 | NAWARANGPUR | 2479.5224 | 259.1311 | 10.45%
24 | NAYAGARH | 1250.08 | 197.2846 | 15.78%
25 | NUAPADA | 1194.7591 | 145.9054 | 12.21%
26 | PURI | 1932.2417 | 100.8786 | 5.221%
27 | RAYAGADA | 1625.114 | 134.9723 | 8.305%
28 | SAMBALPUR | 1270.1463 | 155.7966 | 12.27%
29 | SONEPUR | 758.8284 | 26.2182 | 3.455%
30 | SUNDERGARH | 2820.3379 | 360.1664 | 12.77%
| TOTAL | 59483.4287 | 5952.9888 | 10.01%
4.2) Cooking cost allocation and disbursed to Districts
(Rs. In lakh)
Allocation | OB as on 01.4.17 | Disbursed to Dist | Total Availibility | % Availibility
59483.4287 | 3472.1934 | 55279.8606 | 58752.054 | 98.77%
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2017 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ANGUL | 1619.8882 | 0.16856 | 1603.0641 | 1603.2327 | 98.97%
2 | BALASORE | 3725.9994 | 0 | 3687.4935 | 3687.4935 | 98.97%
3 | BARAGARH | 1844.2384 | 404.7403 | 1407.194 | 1811.9342 | 98.25%
4 | BHADRAK | 2316.6885 | 122.2927 | 2169.5886 | 2291.8812 | 98.93%
5 | BOLANGIR | 2428.2875 | 6.4507 | 2396.6279 | 2403.0786 | 98.96%
6 | BOUDH | 737.5028 | 47.1184 | 681.2216 | 728.34 | 98.76%
7 | CUTTACK | 2357.8189 | 1.2035 | 2333.4961 | 2334.6996 | 99.02%
8 | DEOGARH | 488.4443 | 41.0263 | 440.849 | 481.8754 | 98.66%
9 | DHENKANAL | 1494.0805 | 58.5976 | 1418.1135 | 1476.7111 | 98.84%
10 | GAJAPATI | 1060.8104 | 43.4079 | 1004.1542 | 1047.5621 | 98.75%
11 | GANJAM | 4484.4702 | 568.5186 | 3850.8616 | 4419.3801 | 98.55%
12 | JAGATSINGHPUR | 1191.3818 | 197.4903 | 974.9936 | 1172.484 | 98.41%
13 | JAJPUR | 2484.118 | 0.46314 | 2457.6404 | 2458.1036 | 98.95%
14 | JHARSUGUDA | 561.0904 | 78.2297 | 474.5531 | 552.7828 | 98.52%
15 | KALAHANDI | 2708.4562 | 47.5345 | 2631.0978 | 2678.6322 | 98.9%
16 | KANDHAMAL | 1557.2872 | 93.7443 | 1443.4116 | 1537.1558 | 98.71%
17 | KENDRAPARA | 1891.7545 | 657.6526 | 1191.5349 | 1849.1875 | 97.75%
18 | KEONJHAR | 3001.3339 | 106.5355 | 2851.6408 | 2958.1763 | 98.56%
19 | KHURDHA | 1919.6105 | 29.7803 | 1869.137 | 1898.9173 | 98.92%
20 | KORAPUT | 2273.3651 | 0 | 2248.1105 | 2248.1105 | 98.89%
21 | MALKANGIRI | 1271.0587 | 9.4659 | 1246.7849 | 1256.2508 | 98.83%
22 | MAYURBHANJ | 4734.7137 | 103.3279 | 4568.5512 | 4671.8791 | 98.67%
23 | NAWARANGPUR | 2479.5224 | 186.0893 | 2270.8667 | 2456.9559 | 99.09%
24 | NAYAGARH | 1250.08 | 137.3395 | 1095.6058 | 1232.9453 | 98.63%
25 | NUAPADA | 1194.7591 | 7.3998 | 1175.5109 | 1182.9107 | 99.01%
26 | PURI | 1932.2417 | 52.4351 | 1870.0214 | 1922.4565 | 99.49%
27 | RAYAGADA | 1625.114 | 42.5208 | 1563.2194 | 1605.7402 | 98.81%
28 | SAMBALPUR | 1270.1463 | 407.8959 | 834.6072 | 1242.5031 | 97.82%
29 | SONEPUR | 758.8284 | 20.7644 | 729.253 | 750.0174 | 98.84%
30 | SUNDERGARH | 2820.3379 | 0 | 2790.6563 | 2790.6563 | 98.95%
| TOTAL | 59483.4287 | 3472.1934 | 55279.8606 | 58752.054 | 98.77%
4.4) Cooking Cost Utilisation |  |  |  | (Rs. In lakh)
Allocation | Total available | % available | Utilisation | % Utilisation
59483.4287 | 58752.054 | 98.77% | 52799.0652 | 88.76%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2018-19)
(Rs. In lakh)
S.No. | Name of District | Allocation | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | ANGUL | 1619.8882 | 1526.8028 | 94.25%
2 | BALASORE | 3725.9994 | 3355.5163 | 90.06%
3 | BARAGARH | 1844.2384 | 1666.8118 | 90.38%
4 | BHADRAK | 2316.6885 | 2004.4567 | 86.52%
5 | BOLANGIR | 2428.2875 | 2019.1812 | 83.15%
6 | BOUDH | 737.5028 | 603.2741 | 81.8%
7 | CUTTACK | 2357.8189 | 2058.0437 | 87.29%
8 | DEOGARH | 488.4443 | 439.4058 | 89.96%
9 | DHENKANAL | 1494.0805 | 1386.3408 | 92.79%
10 | GAJAPATI | 1060.8104 | 850.6926 | 80.19%
11 | GANJAM | 4484.4702 | 3952.1343 | 88.13%
12 | JAGATSINGHPUR | 1191.3818 | 1042.2767 | 87.48%
13 | JAJPUR | 2484.118 | 2237.5467 | 90.07%
14 | JHARSUGUDA | 561.0904 | 487.3579 | 86.86%
15 | KALAHANDI | 2708.4562 | 2361.716 | 87.2%
16 | KANDHAMAL | 1557.2872 | 1279.0285 | 82.13%
17 | KENDRAPARA | 1891.7545 | 1702.4359 | 89.99%
18 | KEONJHAR | 3001.3339 | 2616.7908 | 87.19%
19 | KHURDHA | 1919.6105 | 1721.0201 | 89.65%
20 | KORAPUT | 2273.3651 | 2091.1105 | 91.98%
21 | MALKANGIRI | 1271.0587 | 1174.2169 | 92.38%
22 | MAYURBHANJ | 4734.7137 | 4419.0727 | 93.33%
23 | NAWARANGPUR | 2479.5224 | 2197.8248 | 88.64%
24 | NAYAGARH | 1250.08 | 1035.6607 | 82.85%
25 | NUAPADA | 1194.7591 | 1037.0054 | 86.8%
26 | PURI | 1932.2417 | 1821.5779 | 94.27%
27 | RAYAGADA | 1625.114 | 1470.7679 | 90.5%
28 | SAMBALPUR | 1270.1463 | 1086.7066 | 85.56%
29 | SONEPUR | 758.8284 | 723.7992 | 95.38%
30 | SUNDERGARH | 2820.3379 | 2430.4899 | 86.18%
| TOTAL | 59483.4287 | 52799.0652 | 88.76%
5. Reconciliation of Utilisation and Performance during 2017-18 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | ANGUL | 94.26% | 94.25% | -0.002069%
2 | BALASORE | 90.07% | 90.06% | -0.009442%
3 | BARAGARH | 90.4% | 90.38% | -0.01995%
4 | BHADRAK | 86.55% | 86.52% | -0.02742%
5 | BOLANGIR | 83.16% | 83.15% | -0.004299%
6 | BOUDH | 81.81% | 81.8% | -0.007968%
7 | CUTTACK | 87.29% | 87.29% | -0.006215%
8 | DEOGARH | 89.97% | 89.96% | -0.008061%
9 | DHENKANAL | 92.79% | 92.79% | 0.0001403%
10 | GAJAPATI | 80.2% | 80.19% | -0.004028%
11 | GANJAM | 88.15% | 88.13% | -0.01708%
12 | JAGATSINGHPUR | 87.49% | 87.48% | -0.003525%
13 | JAJPUR | 90.09% | 90.07% | -0.01177%
14 | JHARSUGUDA | 86.86% | 86.86% | -0.001216%
15 | KALAHANDI | 87.21% | 87.2% | -0.01299%
16 | KANDHAMAL | 82.16% | 82.13% | -0.02337%
17 | KENDRAPARA | 90% | 89.99% | -0.01002%
18 | KEONJHAR | 87.2% | 87.19% | -0.01416%
19 | KHURDHA | 89.67% | 89.65% | -0.01853%
20 | KORAPUT | 91.98% | 91.98% | -0.0007191%
21 | MALKANGIRI | 92.38% | 92.38% | -0.000969%
22 | MAYURBHANJ | 93.34% | 93.33% | -0.009829%
23 | NAWARANGPUR | 88.67% | 88.64% | -0.02605%
24 | NAYAGARH | 82.85% | 82.85% | 0.0005534%
25 | NUAPADA | 86.81% | 86.8% | -0.01728%
26 | PURI | 94.26% | 94.27% | 0.009053%
27 | RAYAGADA | 90.5% | 90.5% | 0.005457%
28 | SAMBALPUR | 85.58% | 85.56% | -0.02426%
29 | SONEPUR | 95.39% | 95.38% | -0.006902%
30 | SUNDERGARH | 86.2% | 86.18% | -0.01869%
| TOTAL | 88.77% | 88.76% | 0%
5.2 Reconciliation of Food grains utilisation during 2017-18 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 2017-18 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | ANGUL | 28034537 | 3343.056 | 3343.056 | 100%
2 | BALASORE | 61463361 | 7347.4346 | 7347.4347 | 100%
3 | BARAGARH | 30266702 | 3650.2186 | 3650.2186 | 100%
4 | BHADRAK | 36383963 | 4389.6656 | 4389.6656 | 100%
5 | BOLANGIR | 37026411 | 4421.2445 | 4421.2446 | 100%
6 | BOUDH | 11018200 | 1321.0212 | 1321.0212 | 100%
7 | CUTTACK | 37270373 | 4507.1719 | 4507.1719 | 100%
8 | DEOGARH | 7940229 | 962.3414 | 962.3415 | 100%
9 | DHENKANAL | 25408032 | 3035.5876 | 3035.5876 | 100%
10 | GAJAPATI | 16120491 | 1861.7694 | 1861.7694 | 100%
11 | GANJAM | 71395008 | 8655.5963 | 8655.5963 | 100%
12 | JAGATSINGHPUR | 18927226 | 2282.522 | 2282.522 | 100%
13 | JAJPUR | 41221096 | 4899.044 | 4899.0439 | 100%
14 | JHARSUGUDA | 8874302 | 1067.2411 | 1067.2411 | 100%
15 | KALAHANDI | 43512387 | 5170.9024 | 5170.9024 | 100%
16 | KANDHAMAL | 23910718 | 2799.7775 | 2799.7775 | 100%
17 | KENDRAPARA | 31190228 | 3727.7417 | 3727.7417 | 100%
18 | KEONJHAR | 48706806 | 5728.5007 | 5728.5008 | 100%
19 | KHURDHA | 31266005 | 3768.9052 | 3768.9052 | 100%
20 | KORAPUT | 40231171 | 4575.3903 | 4575.3903 | 100%
21 | MALKANGIRI | 22855882 | 2568.7381 | 2568.7381 | 100%
22 | MAYURBHANJ | 81521807 | 9675.234 | 9675.234 | 100%
23 | NAWARANGPUR | 41049711 | 4811.0779 | 4811.0779 | 100%
24 | NAYAGARH | 18803020 | 2268.0406 | 2268.0406 | 100%
25 | NUAPADA | 18797229 | 2271.039 | 2271.0391 | 100%
26 | PURI | 32835955 | 3989.5758 | 3989.5758 | 100%
27 | RAYAGADA | 28270868 | 3218.1139 | 3218.1139 | 100%
28 | SAMBALPUR | 19774817 | 2379.7483 | 2379.7482 | 100%
29 | SONEPUR | 13218687 | 1584.9427 | 1584.9427 | 100%
30 | SUNDERGARH | 44662209 | 5321.6892 | 5321.6892 | 100%
| TOTAL | 971957431 | 115603.3317 | 115603.3316 | 100%
5.3 Reconciliation of Cooking Cost utilisation during 2017-18 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 2017-18 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | ANGUL | 28034537 | 1526.8028 | 1526.8028 | 100%
2 | BALASORE | 61463361 | 3355.5163 | 3355.5163 | 100%
3 | BARAGARH | 30266702 | 1666.8118 | 1666.8118 | 100%
4 | BHADRAK | 36383963 | 2004.4567 | 2004.4567 | 100%
5 | BOLANGIR | 37026411 | 2019.1812 | 2019.1812 | 100%
6 | BOUDH | 11018200 | 603.2741 | 603.2741 | 100%
7 | CUTTACK | 37270373 | 2058.0437 | 2058.0437 | 100%
8 | DEOGARH | 7940229 | 439.4058 | 439.4058 | 100%
9 | DHENKANAL | 25408032 | 1386.3408 | 1386.3408 | 100%
10 | GAJAPATI | 16120491 | 850.6926 | 850.6926 | 100%
11 | GANJAM | 71395008 | 3952.1343 | 3952.1343 | 100%
12 | JAGATSINGHPUR | 18927226 | 1042.2767 | 1042.2767 | 100%
13 | JAJPUR | 41221096 | 2237.5467 | 2237.5467 | 100%
14 | JHARSUGUDA | 8874302 | 487.3579 | 487.3579 | 100%
15 | KALAHANDI | 43512387 | 2361.716 | 2361.716 | 100%
16 | KANDHAMAL | 23910718 | 1279.0285 | 1279.0285 | 100%
17 | KENDRAPARA | 31190228 | 1702.4359 | 1702.4359 | 100%
18 | KEONJHAR | 48706806 | 2616.7908 | 2616.7908 | 100%
19 | KHURDHA | 31266005 | 1721.0201 | 1721.0201 | 100%
20 | KORAPUT | 40231171 | 2091.1105 | 2091.1105 | 100%
21 | MALKANGIRI | 22855882 | 1174.2169 | 1174.2169 | 100%
22 | MAYURBHANJ | 81521807 | 4419.0727 | 4419.0727 | 100%
23 | NAWARANGPUR | 41049711 | 2197.8248 | 2197.8248 | 100%
24 | NAYAGARH | 18803020 | 1035.6607 | 1035.6607 | 100%
25 | NUAPADA | 18797229 | 1037.0054 | 1037.0054 | 100%
26 | PURI | 32835955 | 1821.5779 | 1821.5779 | 100%
27 | RAYAGADA | 28270868 | 1470.7679 | 1470.7679 | 100%
28 | SAMBALPUR | 19774817 | 1086.7066 | 1086.7066 | 100%
29 | SONEPUR | 13218687 | 723.7992 | 723.7992 | 100%
30 | SUNDERGARH | 44662209 | 2430.4899 | 2430.4899 | 100%
| TOTAL | 971957431 | 52799.0652 | 52799.0652 | 100%
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise number of cook-cum-Helpers approved by PAB and engaged by State
(Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | PAB Approval | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | ANGUL | 4281 | 3587 | -694
2 | BALASORE | 7857 | 6116 | -1741
3 | BARAGARH | 4575 | 3680 | -895
4 | BHADRAK | 5336 | 4372 | -964
5 | BOLANGIR | 5925 | 4669 | -1256
6 | BOUDH | 1928 | 1524 | -404
7 | CUTTACK | 6021 | 5095 | -926
8 | DEOGARH | 1495 | 1075 | -420
9 | DHENKANAL | 3983 | 3349 | -634
10 | GAJAPATI | 2896 | 2592 | -304
11 | GANJAM | 10198 | 7566 | -2632
12 | JAGATSINGHPUR | 3210 | 2701 | -509
13 | JAJPUR | 6136 | 5435 | -701
14 | JHARSUGUDA | 1864 | 1409 | -455
15 | KALAHANDI | 6097 | 5230 | -867
16 | KANDHAMAL | 4707 | 3564 | -1143
17 | KENDRAPARA | 5090 | 4061 | -1029
18 | KEONJHAR | 6892 | 5861 | -1031
19 | KHURDHA | 4407 | 3341 | -1066
20 | KORAPUT | 5567 | 5646 | 79
21 | MALKANGIRI | 3128 | 2810 | -318
22 | MAYURBHANJ | 10830 | 8799 | -2031
23 | NAWARANGPUR | 4992 | 4340 | -652
24 | NAYAGARH | 3188 | 2589 | -599
25 | NUAPADA | 2727 | 2264 | -463
26 | PURI | 5330 | 4419 | -911
27 | RAYAGADA | 4447 | 3945 | -502
28 | SAMBALPUR | 3335 | 2765 | -570
29 | SONEPUR | 2324 | 1835 | -489
30 | SUNDERGARH | 6756 | 5312 | -1444
| TOTAL | 145522 | 119951 | -25571
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2018-19)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2017 | Amount released | Total availability | % Availibilty
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | ANGUL | 428.1 | 0 | 452.0768 | 452.0768 | 105.6%
2 | BALASORE | 785.7 | 0 | 817.0506 | 817.0506 | 104%
3 | BARAGARH | 457.5 | 0 | 476.8605 | 476.8605 | 104.2%
4 | BHADRAK | 533.6 | 0 | 558.6841 | 558.6841 | 104.7%
5 | BOLANGIR | 592.5 | 0 | 618.1954 | 618.1954 | 104.3%
6 | BOUDH | 192.8 | 0 | 201.3618 | 201.3618 | 104.4%
7 | CUTTACK | 602.1 | 0 | 633.8202 | 633.8202 | 105.3%
8 | DEOGARH | 149.5 | 0 | 153.1359 | 153.1359 | 102.4%
9 | DHENKANAL | 398.3 | 0 | 417.9888 | 417.9888 | 104.9%
10 | GAJAPATI | 289.6 | 0 | 305.4415 | 305.4415 | 105.5%
11 | GANJAM | 1019.8 | 0 | 1026.67 | 1026.67 | 100.7%
12 | JAGATSINGHPUR | 321 | 0 | 337.582 | 337.582 | 105.2%
13 | JAJPUR | 613.6 | 0 | 650.3265 | 650.3265 | 106%
14 | JHARSUGUDA | 186.4 | 0 | 192.599 | 192.599 | 103.3%
15 | KALAHANDI | 609.7 | 0 | 644.0421 | 644.0421 | 105.6%
16 | KANDHAMAL | 470.7 | 0 | 485.3374 | 485.3374 | 103.1%
17 | KENDRAPARA | 509 | 0 | 531.1533 | 531.1533 | 104.4%
18 | KEONJHAR | 689.2 | 0 | 726.535 | 726.535 | 105.4%
19 | KHURDHA | 440.7 | 0 | 455.5323 | 455.5323 | 103.4%
20 | KORAPUT | 556.7 | 0 | 630.68 | 630.68 | 113.3%
21 | MALKANGIRI | 312.8 | 0 | 332.2176 | 332.2176 | 106.2%
22 | MAYURBHANJ | 1083 | 0 | 1133.6569 | 1133.6569 | 104.7%
23 | NAWARANGPUR | 499.2 | 0 | 528.2413 | 528.2413 | 105.8%
24 | NAYAGARH | 318.8 | 0 | 330.4248 | 330.4248 | 103.6%
25 | NUAPADA | 272.7 | 0 | 286.2656 | 286.2656 | 105%
26 | PURI | 533 | 0 | 558.2948 | 558.2948 | 104.7%
27 | RAYAGADA | 444.7 | 0 | 470.3775 | 470.3775 | 105.8%
28 | SAMBALPUR | 333.5 | 0 | 349.2708 | 349.2708 | 104.7%
29 | SONEPUR | 232.4 | 0 | 241.062 | 241.062 | 103.7%
30 | SUNDERGARH | 675.6 | 0 | 701.0922 | 701.0922 | 103.8%
| TOTAL | 14552.2 | 0 | 15245.9763 | 15245.9763 | 104.8%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | Allocation | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | ANGUL | 428.1 | 452.0768 | 412.3381 | 96.32%
2 | BALASORE | 785.7 | 817.0506 | 685.0222 | 87.19%
3 | BARAGARH | 457.5 | 476.8605 | 405.6933 | 88.68%
4 | BHADRAK | 533.6 | 558.6841 | 487.4111 | 91.34%
5 | BOLANGIR | 592.5 | 618.1954 | 530.7209 | 89.57%
6 | BOUDH | 192.8 | 201.3618 | 172.0194 | 89.22%
7 | CUTTACK | 602.1 | 633.8202 | 582.4991 | 96.74%
8 | DEOGARH | 149.5 | 153.1359 | 125.5563 | 83.98%
9 | DHENKANAL | 398.3 | 417.9888 | 369.4417 | 92.75%
10 | GAJAPATI | 289.6 | 305.4415 | 279.5068 | 96.51%
11 | GANJAM | 1019.8 | 1026.67 | 846.886 | 83.04%
12 | JAGATSINGHPUR | 321 | 337.582 | 294.4806 | 91.74%
13 | JAJPUR | 613.6 | 650.3265 | 596.3682 | 97.19%
14 | JHARSUGUDA | 186.4 | 192.599 | 157.504 | 84.5%
15 | KALAHANDI | 609.7 | 644.0421 | 591.9677 | 97.09%
16 | KANDHAMAL | 470.7 | 485.3374 | 394.8489 | 83.89%
17 | KENDRAPARA | 509 | 531.1533 | 459.8263 | 90.34%
18 | KEONJHAR | 689.2 | 726.535 | 662.8865 | 96.18%
19 | KHURDHA | 440.7 | 455.5323 | 367.2975 | 83.34%
20 | KORAPUT | 556.7 | 630.68 | 626.6825 | 112.6%
21 | MALKANGIRI | 312.8 | 332.2176 | 311.6003 | 99.62%
22 | MAYURBHANJ | 1083 | 1133.6569 | 981.2411 | 90.6%
23 | NAWARANGPUR | 499.2 | 528.2413 | 482.9447 | 96.74%
24 | NAYAGARH | 318.8 | 330.4248 | 275.0963 | 86.29%
25 | NUAPADA | 272.7 | 286.2656 | 255.7848 | 93.8%
26 | PURI | 533 | 558.2948 | 492.9846 | 92.49%
27 | RAYAGADA | 444.7 | 470.3775 | 433.7545 | 97.54%
28 | SAMBALPUR | 333.5 | 349.2708 | 306.3201 | 91.85%
29 | SONEPUR | 232.4 | 241.062 | 210.9158 | 90.76%
30 | SUNDERGARH | 675.6 | 701.0922 | 587.6017 | 86.97%
| TOTAL | 14552.2 | 15245.9763 | 13387.201 | 91.99%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A,AWP&B, 2018-19)
S.No. | Name of District | Allocation | Total Availability | Unspent balance as on 31.03.2018 | % of UB as on Allocation
1 | 2 | 3 | 4 | 5 | 6
1 | ANGUL | 428.1 | 452.0768 | 39.7387 | 9.283%
2 | BALASORE | 785.7 | 817.0506 | 132.0284 | 16.8%
3 | BARAGARH | 457.5 | 476.8605 | 71.1673 | 15.56%
4 | BHADRAK | 533.6 | 558.6841 | 71.273 | 13.36%
5 | BOLANGIR | 592.5 | 618.1954 | 87.4745 | 14.76%
6 | BOUDH | 192.8 | 201.3618 | 29.3423 | 15.22%
7 | CUTTACK | 602.1 | 633.8202 | 51.3211 | 8.524%
8 | DEOGARH | 149.5 | 153.1359 | 27.5796 | 18.45%
9 | DHENKANAL | 398.3 | 417.9888 | 48.5471 | 12.19%
10 | GAJAPATI | 289.6 | 305.4415 | 25.9346 | 8.955%
11 | GANJAM | 1019.8 | 1026.67 | 179.784 | 17.63%
12 | JAGATSINGHPUR | 321 | 337.582 | 43.1014 | 13.43%
13 | JAJPUR | 613.6 | 650.3265 | 53.9583 | 8.794%
14 | JHARSUGUDA | 186.4 | 192.599 | 35.095 | 18.83%
15 | KALAHANDI | 609.7 | 644.0421 | 52.0744 | 8.541%
16 | KANDHAMAL | 470.7 | 485.3374 | 90.4885 | 19.22%
17 | KENDRAPARA | 509 | 531.1533 | 71.3269 | 14.01%
18 | KEONJHAR | 689.2 | 726.535 | 63.6484 | 9.235%
19 | KHURDHA | 440.7 | 455.5323 | 88.2348 | 20.02%
20 | KORAPUT | 556.7 | 630.68 | 3.9975 | 0.7181%
21 | MALKANGIRI | 312.8 | 332.2176 | 20.6173 | 6.591%
22 | MAYURBHANJ | 1083 | 1133.6569 | 152.4159 | 14.07%
23 | NAWARANGPUR | 499.2 | 528.2413 | 45.2966 | 9.074%
24 | NAYAGARH | 318.8 | 330.4248 | 55.3284 | 17.36%
25 | NUAPADA | 272.7 | 286.2656 | 30.4808 | 11.18%
26 | PURI | 533 | 558.2948 | 65.3102 | 12.25%
27 | RAYAGADA | 444.7 | 470.3775 | 36.6229 | 8.235%
28 | SAMBALPUR | 333.5 | 349.2708 | 42.9507 | 12.88%
29 | SONEPUR | 232.4 | 241.062 | 30.1462 | 12.97%
30 | SUNDERGARH | 675.6 | 701.0922 | 113.4905 | 16.8%
| TOTAL | 14552.2 | 15245.9763 | 1858.7753 | 12.77%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 825.66 | 825.66 | 0 | 0%
2 | Opening Balance as on 01.04.2017 | 0 | 0 | 0 | #DIV/0!
3 | Released during 2017-18. | 819.59 | 819.59 | 0 | 0%
4 | Total Availibility | 819.59 | 819.59 | 0 | 0%
7.2) Utilisation of MME during 2017-18 (Source data: Table AT-10 of AWP&B 2018-19)
|  |  |  | (Rs. In lakh) | (As on 31.03.18)
Sl. No. | Activity | Allocated | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 412.83 | 409.8 | 409.8 | 99.27%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 412.83 | 409.79 | 409.79 | 99.26%
Total |  | 825.66 | 819.59 | 819.59 | 99.26%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2017-18 | 976.67 | 976.67 | 0 | 0%
2 | Opening Balance as on 01.04.2017 | 15.36 | 15.36 | 0 | 0%
3 | Released during 2017-18. | 802.2 | 802.2 | 0 | 0%
4 | Total Availibility | 817.56 | 817.56 | 0 | 0%
8.2) Utilisation of TA during 2017-18 (Source data: Table AT-9 of AWP&B 2018-19)
(Rs. In lakh)
Allocated for 2016-17 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
976.67 | 817.56 | 116646.3946 | 874.848 | 749.81 | 125.038 | 76.77% | 67.75
9. INFRASTRUCTURE DEVELOPMENT DURING 2017-18 (Primary + Upper primary) | [8 empty] | 5
Kitchen Sheds
9.1) Releasing details
9054.6
Releases for Kitchen sheds by GoI as on 31.03.2018 | [7 empty] | 15791.4
Schools | Installment | Dated | Units | Amount (in lakh) |  |  |  | 11249.4
Primary & Upper Primary | 2006-07 |  | 15091 | 9054.33 |  |  |  | 5395.8
| 2007-08 |  | 26319 | 15791.4
| 2008-09 |  | 18749 | 11249.4
| 2009-10 |  | 8993 | 4484.68
| 2010-11 |  | 0 | 0
| 2011-12 |  | 0 | 0
| 2012-13 |  | 0 | 0
| 2013-14 |  | 0 | 0
| Total |  | 69152 | 40579.81
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-17 | 69152 | 40579.81 | 69152 | 40579.81 | 0% | 0%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2018-19)
Sactioned by GoI during 2006-07 to 2017-18 |  | Achievement Completed upto 31.03.2018 |  | Achievement as % of allocation |  |  |  |  | 69152 | 40579.81 | 43354 | 26012.4 | 25798 | 14567.41 | 0 | 0
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
69152 | 40579.81 | 43354 | 26012.4 | 62.69% | 64.1%
10. Kitchen Devices
10.1) Releasing details
Releases for Kitchen devices by GoI as on 31.03.2018
Schools | Installment | Dated | Units | Amount (in lakh)
Primary+Upper Primary | 2006-07 |  | 34385 | 1719.25
| 2007-08 |  | 18343 | 917.15
| 2008-09 |  | 10977 | 548.85
| 2009-10 |  | 2678 | 133.9
| 2010-11 |  | 0 | 0
| 2011-12 |  | 0 | 0
| 2012-13 |  | 0 | 0
| 2013-14 |  | 54228 | 2711.4 | New | 67882
| 2014-15 |  | 10977 | 548.85 | Rep | 66384
| 2016-17 |  | 2678 | 133.9
| Total |  | 134266 | 6713.3
10.2 Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-17 | 134266 | 6713.3 | 134266 | 6713.3 | 0% | -1.355e-14%
8.6) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2017-18)
Sactioned during 2006-07 to 2017-18 |  | Achievement (C) upto 31.03.2018 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
134266 | 6713.3 | 134266 | 6713.3 | 100% | 100%
Benchmark (85%)
100%
68%
Note on E972: hp: pl chek