## Gujarat
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget (AWP&B) 2020-21
State : Gujarat
Part-D: ANALYSIS SHEET
Section-A : REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2019-20
1. Calculation of Bench mark for utilisation.
1.1) No. of children
Stage | MDM PAB Approval for 2019-20 | Average number of children availed MDM during 2019-20 | Diff | Diff in %
Primary | 2605009 | 2523852 | -81157 | -3.115%
Up Primary | 1694020 | 1473776 | -220244 | -13%
NCLP | 0 | 0 | 0 | 0%
Total | 4299029 | 3997628 | -301401 | -7.011%
1.2) No. of School working days
PY | 248 | 243 | -5 | -2.016%
UP.PY | 248 | 243 | -5 | -2.016%
NCLP | 0 | 0 | 0 | 0%
1.3) Number of meals served vis-à-vis PAB approval during 2019-20
Stage | No. of Meals as per PAB approval | No. of Meals claimed to have served by the State | Diff. | Diff in %
PY | 646042232 | 613296036 | -32746196 | -5.069%
UP PY | 420116960 | 358127568 | -61989392 | -14.76%
NCLP | 0 | 0 | 0 | 0%
Total | 1066159192 | 971423604 | -94735588 | -8.886%
2. COVERAGE
2.1 Institutions- (Primary) (Source data : Table AT-3A of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ahmedabad | 152 | 152 | 0 | 0%
2 | Amreli | 58 | 58 | 0 | 0%
3 | Anand | 453 | 453 | 0 | 0%
4 | Arvalli | 547 | 547 | 0 | 0%
5 | Banaskantha | 1009 | 1009 | 0 | 0%
6 | Bharuch | 258 | 258 | 0 | 0%
7 | Bhavnagar | 80 | 80 | 0 | 0%
8 | Botad | 14 | 14 | 0 | 0%
9 | Chotta udepur | 834 | 834 | 0 | 0%
10 | Dahod | 808 | 808 | 0 | 0%
11 | Dangs | 254 | 254 | 0 | 0%
12 | Dev bhumi dwarka | 121 | 121 | 0 | 0%
13 | Gandhinagar | 124 | 124 | 0 | 0%
14 | Gir somnath | 56 | 56 | 0 | 0%
15 | Jamnagar | 27 | 27 | 0 | 0%
16 | Junagadh | 106 | 106 | 0 | 0%
17 | Kheda-Nadiad | 625 | 625 | 0 | 0%
18 | Kutch-Bhuj | 235 | 235 | 0 | 0%
19 | Mahisagar | 680 | 680 | 0 | 0%
20 | Mehsana | 219 | 219 | 0 | 0%
21 | Morbi | 44 | 44 | 0 | 0%
22 | Narmda | 322 | 322 | 0 | 0%
23 | Navsari | 273 | 273 | 0 | 0%
24 | Panchmahals | 618 | 618 | 0 | 0%
25 | Patan | 188 | 188 | 0 | 0%
26 | Porbandar | 62 | 62 | 0 | 0%
27 | Rajkot | 48 | 48 | 0 | 0%
28 | Sabarkantha | 446 | 446 | 0 | 0%
29 | Surat | 528 | 528 | 0 | 0%
30 | Surendranagar | 104 | 104 | 0 | 0%
31 | Tapi | 483 | 483 | 0 | 0%
32 | Vadodara | 542 | 542 | 0 | 0%
33 | Valsad | 440 | 440 | 0 | 0%
| TOTAL | 10758 | 10758 | 0 | 0%
2.2 Institutions- (Primary with Upper Primary) (Source data : Table AT-3B of AWP&B 2020-21)
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ahmedabad | 1084 | 1084 | 0 | 0
2 | Amreli | 774 | 774 | 0 | 0
3 | Anand | 625 | 625 | 0 | 0
4 | Arvalli | 715 | 715 | 0 | 0
5 | Banaskantha | 1662 | 1662 | 0 | 0
6 | Bharuch | 683 | 683 | 0 | 0
7 | Bhavnagar | 1017 | 1017 | 0 | 0
8 | Botad | 236 | 236 | 0 | 0
9 | Chotta udepur | 462 | 462 | 0 | 0
10 | Dahod | 911 | 911 | 0 | 0
11 | Dangs | 261 | 261 | 0 | 0
12 | Dev bhumi dwarka | 527 | 527 | 0 | 0
13 | Gandhinagar | 553 | 553 | 0 | 0
14 | Gir somnath | 516 | 516 | 0 | 0
15 | Jamnagar | 758 | 758 | 0 | 0
16 | Junagadh | 716 | 716 | 0 | 0
17 | Kheda-Nadiad | 810 | 810 | 0 | 0
18 | Kutch-Bhuj | 1656 | 1656 | 0 | 0
19 | Mahisagar | 464 | 464 | 0 | 0
20 | Mehsana | 828 | 828 | 0 | 0
21 | Morbi | 569 | 569 | 0 | 0
22 | Narmda | 376 | 376 | 0 | 0
23 | Navsari | 467 | 467 | 0 | 0
24 | Panchmahals | 765 | 765 | 0 | 0
25 | Patan | 683 | 683 | 0 | 0
26 | Porbandar | 267 | 267 | 0 | 0
27 | Rajkot | 1001 | 1001 | 0 | 0
28 | Sabarkantha | 907 | 907 | 0 | 0
29 | Surat | 868 | 868 | 0 | 0
30 | Surendranagar | 809 | 809 | 0 | 0
31 | Tapi | 332 | 332 | 0 | 0
32 | Vadodara | 831 | 831 | 0 | 0
33 | Valsad | 551 | 551 | 0 | 0
| TOTAL | 23684 | 23684 | 0 | 0
2.2A Institutions- (Upper Primary) (Source data : Table AT-3C of AWP&B 2020-21) | [7 empty] | 24030
Sl. No. | Districts | No. of Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | 2 | 3 | 4 | 5=3-4 | 6
1 | Ahmedabad | 15 | 15 | 0 | 0%
2 | Amreli | 4 | 4 | 0 | 0%
3 | Anand | 13 | 13 | 0 | 0%
4 | Arvalli | 12 | 12 | 0 | 0%
5 | Banaskantha | 0 | 0 | 0 | 0%
6 | Bharuch | 12 | 12 | 0 | 0%
7 | Bhavnagar | 4 | 4 | 0 | 0%
8 | Botad | 2 | 2 | 0 | 0%
9 | Chotta udepur | 10 | 10 | 0 | 0%
10 | Dahod | 3 | 3 | 0 | 0%
11 | Dangs | 0 | 0 | 0 | 0%
12 | Dev bhumi dwarka | 0 | 0 | 0 | 0%
13 | Gandhinagar | 2 | 2 | 0 | 0%
14 | Gir somnath | 0 | 0 | 0 | 0%
15 | Jamnagar | 0 | 0 | 0 | 0%
16 | Junagadh | 0 | 0 | 0 | 0%
17 | Kheda-Nadiad | 10 | 10 | 0 | 0%
18 | Kutch-Bhuj | 1 | 1 | 0 | 0%
19 | Mahisagar | 0 | 0 | 0 | 0%
20 | Mehsana | 3 | 3 | 0 | 0%
21 | Morbi | 26 | 26 | 0 | 0%
22 | Narmda | 0 | 0 | 0 | 0%
23 | Navsari | 2 | 2 | 0 | 0%
24 | Panchmahals | 110 | 110 | 0 | 0%
25 | Patan | 5 | 5 | 0 | 0%
26 | Porbandar | 0 | 0 | 0 | 0%
27 | Rajkot | 1 | 1 | 0 | 0%
28 | Sabarkantha | 37 | 37 | 0 | 0%
29 | Surat | 8 | 8 | 0 | 0%
30 | Surendranagar | 41 | 41 | 0 | 0%
31 | Tapi | 4 | 4 | 0 | 0%
32 | Vadodara | 20 | 20 | 0 | 0%
33 | Valsad | 1 | 1 | 0 | 0%
| TOTAL | 346 | 346 | 0 | 0%
2.3 Coverage Chidlren vs. Enrolment ( Primary) (Source data : Table AT-4 & 5 of AWP&B 2020-21)
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff
1 | 2 | 3 | 4 | 5=4-3 | 6
1 | Ahmedabad | 191222 | 137918 | -53304 | -27.88% |  | 72.1245
2 | Amreli | 79810 | 51320 | -28490 | -35.7% |  | 64.3027
3 | Anand | 124762 | 93581 | -31181 | -24.99% |  | 75.0076
4 | Arvalli | 76850 | 65938 | -10912 | -14.2% |  | 85.8009
5 | Banaskantha | 293370 | 221246 | -72124 | -24.58% |  | 75.4153
6 | Bharuch | 70853 | 59117 | -11736 | -16.56% |  | 83.4361
7 | Bhavnagar | 141779 | 99467 | -42312 | -29.84% |  | 70.1564
8 | Botad | 43858 | 29757 | -14101 | -32.15% |  | 67.8485
9 | Chotta udepur | 77397 | 74794 | -2603 | -3.363% |  | 96.6368
10 | Dahod | 228044 | 197410 | -30634 | -13.43% |  | 86.5666
11 | Dangs | 29847 | 25075 | -4772 | -15.99% |  | 84.0118
12 | Dev bhumi dwarka | 43082 | 31993 | -11089 | -25.74% |  | 74.2607
13 | Gandhinagar | 73647 | 58520 | -15127 | -20.54% |  | 79.4601
14 | Gir somnath | 68279 | 44859 | -23420 | -34.3% |  | 65.6996
15 | Jamnagar | 58473 | 53298 | -5175 | -8.85% |  | 91.1498
16 | Junagadh | 46963 | 26969 | -19994 | -42.57% |  | 57.4261
17 | Kheda-Nadiad | 139103 | 112202 | -26901 | -19.34% |  | 80.6611
18 | Kutch-Bhuj | 155437 | 111169 | -44268 | -28.48% |  | 71.5203
19 | Mahisagar | 77574 | 73571 | -4003 | -5.16% |  | 94.8398
20 | Mehsana | 118542 | 77946 | -40596 | -34.25% |  | 65.7539
21 | Morbi | 58688 | 41770 | -16918 | -28.83% |  | 71.173
22 | Narmda | 40801 | 38778 | -2023 | -4.958% |  | 95.0418
23 | Navsari | 50907 | 36363 | -14544 | -28.57% |  | 71.4303
24 | Panchmahals | 132804 | 119519 | -13285 | -10% |  | 89.9965
25 | Patan | 99943 | 69568 | -30375 | -30.39% |  | 69.6077
26 | Porbandar | 22865 | 16196 | -6669 | -29.17% |  | 70.8332
27 | Rajkot | 99049 | 74955 | -24094 | -24.33% |  | 75.6747
28 | Sabarkantha | 108888 | 89658 | -19230 | -17.66% |  | 82.3397
29 | Surat | 173240 | 119742 | -53498 | -30.88% |  | 69.1191
30 | Surendranagar | 102015 | 68672 | -33343 | -32.68% |  | 67.3156
31 | Tapi | 48682 | 45678 | -3004 | -6.171% |  | 93.8293
32 | Vadodara | 104549 | 85405 | -19144 | -18.31% |  | 81.689
33 | Valsad | 86348 | 71398 | -14950 | -17.31% |  | 82.6863
| TOTAL | 3267671 | 2523852 | -743819 | -22.76% |  | 77.237
#DIV/0!
2.4 Coverage Chidlren vs. Enrolment ( Up Pry) (Source : Table AT- 4A & 5-A of AWP&B 2020-21) | [6 empty] | #DIV/0!
Sl. No. | Districts | Enrolment as on 30.9.2019 | Average number of children availing MDM | Diff | % Diff |  | #VALUE!
1 | 2 | 3 | 4 | 5=4-3 | 6 |  | 133.3333
1 | Ahmedabad | 116118 | 92895 | -23223 | -20% |  | 80.0005
2 | Amreli | 47092 | 32964 | -14128 | -30% |  | 69.9992
3 | Anand | 70575 | 51520 | -19055 | -27% |  | 73.0004
4 | Arvalli | 43471 | 33908 | -9563 | -22% |  | 78.0014
5 | Banaskantha | 161456 | 114489 | -46967 | -29.09% |  | 70.9103
6 | Bharuch | 40077 | 32062 | -8015 | -20% |  | 80.001
7 | Bhavnagar | 88976 | 65842 | -23134 | -26% |  | 73.9997
8 | Botad | 25545 | 17882 | -7663 | -30% |  | 70.002
9 | Chotta udepur | 36542 | 32888 | -3654 | -9.999% |  | 90.0005
10 | Dahod | 120392 | 97518 | -22874 | -19% |  | 81.0004
11 | Dangs | 12487 | 11863 | -624 | -4.997% |  | 95.0028
12 | Dev bhumi dwarka | 22290 | 19839 | -2451 | -11% |  | 89.004
13 | Gandhinagar | 53014 | 47713 | -5301 | -9.999% |  | 90.0008
14 | Gir somnath | 50141 | 35099 | -15042 | -30% |  | 70.0006
15 | Jamnagar | 36494 | 31020 | -5474 | -15% |  | 85.0003
16 | Junagadh | 29436 | 17662 | -11774 | -40% |  | 60.0014
17 | Kheda-Nadiad | 84979 | 69683 | -15296 | -18% |  | 82.0003
18 | Kutch-Bhuj | 86769 | 60739 | -26030 | -30% |  | 70.0008
19 | Mahisagar | 44848 | 39915 | -4933 | -11% |  | 89.0006
20 | Mehsana | 71730 | 56666 | -15064 | -21% |  | 78.999
21 | Morbi | 29239 | 21929 | -7310 | -25% |  | 74.9991
22 | Narmda | 20277 | 19263 | -1014 | -5.001% |  | 94.9993
23 | Navsari | 31233 | 24361 | -6872 | -22% |  | 77.9976
24 | Panchmahals | 76705 | 68267 | -8438 | -11% |  | 88.9994
25 | Patan | 61220 | 45302 | -15918 | -26% |  | 73.9987
26 | Porbandar | 14752 | 12539 | -2213 | -15% |  | 84.9986
27 | Rajkot | 56706 | 42529 | -14177 | -25% |  | 74.9991
28 | Sabarkantha | 75496 | 49073 | -26423 | -35% |  | 65.0008
29 | Surat | 103395 | 75478 | -27917 | -27% |  | 72.9997
30 | Surendranagar | 56552 | 44110 | -12442 | -22% |  | 77.999
31 | Tapi | 24227 | 23015 | -1212 | -5.003% |  | 94.9973
32 | Vadodara | 63818 | 47863 | -15955 | -25% |  | 74.9992
33 | Valsad | 48565 | 37880 | -10685 | -22% |  | 77.9986
| TOTAL | 1904617 | 1473776 | -430841 | -22.62% |  | 77.3791
#DIV/0!
#DIV/0!
2.5 No. of children ( Primary) (Source data : Table AT-5 of AWP&B 2020-21) | [6 empty] | #DIV/0!
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff |  | #VALUE!
1 | 2 | 3 | 4 | 5=4-3 | 6 |  | 133.3333
1 | Ahmedabad | 154882 | 137918 | -16964 | -10.95% |  | 89.0471
2 | Amreli | 59905 | 51320 | -8585 | -14.33% |  | 85.669
3 | Anand | 95842 | 93581 | -2261 | -2.359% |  | 97.6409
4 | Arvalli | 68606 | 65938 | -2668 | -3.889% |  | 96.1111
5 | Banaskantha | 235344 | 221246 | -14098 | -5.99% |  | 94.0096
6 | Bharuch | 63398 | 59117 | -4281 | -6.753% |  | 93.2474
7 | Bhavnagar | 110156 | 99467 | -10689 | -9.704% |  | 90.2965
8 | Botad | 37154 | 29757 | -7397 | -19.91% |  | 80.091
9 | Chotta udepur | 74801 | 74794 | -7 | -0.009358% |  | 99.9906
10 | Dahod | 193105 | 197410 | 4305 | 2.229% |  | 102.2294
11 | Dangs | 25955 | 25075 | -880 | -3.39% |  | 96.6095
12 | Dev bhumi dwarka | 31017 | 31993 | 976 | 3.147% |  | 103.1467
13 | Gandhinagar | 63445 | 58520 | -4925 | -7.763% |  | 92.2374
14 | Gir somnath | 48067 | 44859 | -3208 | -6.674% |  | 93.326
15 | Jamnagar | 49769 | 53298 | 3529 | 7.091% |  | 107.0908
16 | Junagadh | 22086 | 26969 | 4883 | 22.11% |  | 122.109
17 | Kheda-Nadiad | 101533 | 112202 | 10669 | 10.51% |  | 110.5079
18 | Kutch-Bhuj | 116568 | 111169 | -5399 | -4.632% |  | 95.3684
19 | Mahisagar | 76848 | 73571 | -3277 | -4.264% |  | 95.7357
20 | Mehsana | 103079 | 77946 | -25133 | -24.38% |  | 75.6177
21 | Morbi | 42574 | 41770 | -804 | -1.888% |  | 98.1115
22 | Narmda | 44393 | 38778 | -5615 | -12.65% |  | 87.3516
23 | Navsari | 34591 | 36363 | 1772 | 5.123% |  | 105.1227
24 | Panchmahals | 117999 | 119519 | 1520 | 1.288% |  | 101.2881
25 | Patan | 80600 | 69568 | -11032 | -13.69% |  | 86.3127
26 | Porbandar | 22799 | 16196 | -6603 | -28.96% |  | 71.0382
27 | Rajkot | 77993 | 74955 | -3038 | -3.895% |  | 96.1048
28 | Sabarkantha | 90707 | 89658 | -1049 | -1.156% |  | 98.8435
29 | Surat | 95701 | 119742 | 24041 | 25.12% |  | 125.1209
30 | Surendranagar | 65139 | 68672 | 3533 | 5.424% |  | 105.4238
31 | Tapi | 45547 | 45678 | 131 | 0.2876% |  | 100.2876
32 | Vadodara | 78220 | 85405 | 7185 | 9.186% |  | 109.1856
33 | Valsad | 77186 | 71398 | -5788 | -7.499% |  | 92.5012
| TOTAL | 2605009 | 2523852 | -81157 | -3.115% |  | 96.8846
#DIV/0!
2.6 No. of children ( Upper Primary) (Source data : Table AT-5-A of AWP&B 2020-21) | [6 empty] | #DIV/0!
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff |  | #VALUE!
1 | 2 | 3 | 4 | 5=4-3 | 6 |  | 133.3333
1 | Ahmedabad | 106014 | 92895 | -13119 | -12.37% |  | 87.6252
2 | Amreli | 37908 | 32964 | -4944 | -13.04% |  | 86.9579
3 | Anand | 63183 | 51520 | -11663 | -18.46% |  | 81.5409
4 | Arvalli | 39254 | 33908 | -5346 | -13.62% |  | 86.381
5 | Banaskantha | 137474 | 114489 | -22985 | -16.72% |  | 83.2805
6 | Bharuch | 41169 | 32062 | -9107 | -22.12% |  | 77.879
7 | Bhavnagar | 79938 | 65842 | -14096 | -17.63% |  | 82.3663
8 | Botad | 25553 | 17882 | -7671 | -30.02% |  | 69.98
9 | Chotta udepur | 38192 | 32888 | -5304 | -13.89% |  | 86.1123
10 | Dahod | 101682 | 97518 | -4164 | -4.095% |  | 95.9049
11 | Dangs | 16087 | 11863 | -4224 | -26.26% |  | 73.7428
12 | Dev bhumi dwarka | 21433 | 19839 | -1594 | -7.437% |  | 92.5629
13 | Gandhinagar | 42067 | 47713 | 5646 | 13.42% |  | 113.4214
14 | Gir somnath | 39453 | 35099 | -4354 | -11.04% |  | 88.9641
15 | Jamnagar | 33102 | 31020 | -2082 | -6.29% |  | 93.7103
16 | Junagadh | 22558 | 17662 | -4896 | -21.7% |  | 78.2959
17 | Kheda-Nadiad | 73325 | 69683 | -3642 | -4.967% |  | 95.0331
18 | Kutch-Bhuj | 74693 | 60739 | -13954 | -18.68% |  | 81.3182
19 | Mahisagar | 46914 | 39915 | -6999 | -14.92% |  | 85.0812
20 | Mehsana | 81121 | 56666 | -24455 | -30.15% |  | 69.8537
21 | Morbi | 24653 | 21929 | -2724 | -11.05% |  | 88.9506
22 | Narmda | 26555 | 19263 | -7292 | -27.46% |  | 72.54
23 | Navsari | 27126 | 24361 | -2765 | -10.19% |  | 89.8068
24 | Panchmahals | 77387 | 68267 | -9120 | -11.78% |  | 88.2151
25 | Patan | 54542 | 45302 | -9240 | -16.94% |  | 83.0589
26 | Porbandar | 20683 | 12539 | -8144 | -39.38% |  | 60.6247
27 | Rajkot | 50677 | 42529 | -8148 | -16.08% |  | 83.9217
28 | Sabarkantha | 52971 | 49073 | -3898 | -7.359% |  | 92.6413
29 | Surat | 75364 | 75478 | 114 | 0.1513% |  | 100.1513
30 | Surendranagar | 39154 | 44110 | 4956 | 12.66% |  | 112.6577
31 | Tapi | 25766 | 23015 | -2751 | -10.68% |  | 89.3231
32 | Vadodara | 54414 | 47863 | -6551 | -12.04% |  | 87.9608
33 | Valsad | 43608 | 37880 | -5728 | -13.14% |  | 86.8648
| TOTAL | 1694020 | 1473776 | -220244 | -13% |  | 86.9987
#DIV/0!
2.7 Number of meal to be served and actual number of meal served during 2019-20 (Source data: Table AT-5 & 5A of AWP&B 2020-21) | [6 empty] | #DIV/0!
Sr. No. | District | No of meals to be served during 2019-20 | No of meal served during 2019-20 | % Meals Served |  |  | #VALUE!
1 | 2 | 3 | 4 | 5 |  |  | 133.3333
1 | Ahmedabad | 64702208 | 56087559 | 86.69% |  |  | 86.6857
2 | Amreli | 24257624 | 20481012 | 84.43% |  |  | 84.4312
3 | Anand | 41953416 | 35259543 | 84.04% |  |  | 84.0445
4 | Arvalli | 32683672 | 24262578 | 74.23% |  |  | 74.2346
5 | Banaskantha | 92458864 | 81583605 | 88.24% |  |  | 88.2377
6 | Bharuch | 25932616 | 22156497 | 85.44% |  |  | 85.4387
7 | Bhavnagar | 33904328 | 40170087 | 118.5% |  |  | 118.4807
8 | Botad | 29038816 | 11576277 | 39.86% |  |  | 39.8648
9 | Chotta udepur | 37074512 | 26166726 | 70.58% |  |  | 70.5787
10 | Dahod | 51879616 | 71667504 | 138.1% |  |  | 138.1419
11 | Dangs | 16869456 | 8975934 | 53.21% |  |  | 53.2082
12 | Dev bhumi dwarka | 26884192 | 12595176 | 46.85% |  |  | 46.8497
13 | Gandhinagar | 40951496 | 25814619 | 63.04% |  |  | 63.0371
14 | Gir somnath | 20129912 | 19429794 | 96.52% |  |  | 96.522
15 | Jamnagar | 17937096 | 20489274 | 114.2% |  |  | 114.2285
16 | Junagadh | 10606712 | 10845333 | 102.2% |  |  | 102.2497
17 | Kheda-Nadiad | 45298192 | 44198055 | 97.57% |  |  | 97.5713
18 | Kutch-Bhuj | 42435280 | 41773644 | 98.44% |  |  | 98.4408
19 | Mahisagar | 31626200 | 27577098 | 87.2% |  |  | 87.197
20 | Mehsana | 38700400 | 32710716 | 84.52% |  |  | 84.5229
21 | Morbi | 29248624 | 15478857 | 52.92% |  |  | 52.9217
22 | Narmda | 20719656 | 14103963 | 68.07% |  |  | 68.0704
23 | Navsari | 22073240 | 14755932 | 66.85% |  |  | 66.8499
24 | Panchmahals | 40078536 | 45631998 | 113.9% |  |  | 113.8564
25 | Patan | 26716048 | 27913410 | 104.5% |  |  | 104.4818
26 | Porbandar | 12044120 | 6982605 | 57.98% |  |  | 57.9752
27 | Rajkot | 29077256 | 28548612 | 98.18% |  |  | 98.1819
28 | Sabarkantha | 28832480 | 33711633 | 116.9% |  |  | 116.9224
29 | Surat | 33205464 | 47438460 | 142.9% |  |  | 142.8634
30 | Surendranagar | 21469856 | 27406026 | 127.6% |  |  | 127.6489
31 | Tapi | 21080000 | 16692399 | 79.19% |  |  | 79.186
32 | Vadodara | 31033232 | 32384124 | 104.4% |  |  | 104.353
33 | Valsad | 25256072 | 26554554 | 105.1% |  |  | 105.1413
| TOTAL | 1066159192 | 971423604 | 91.11% |  |  | 91.1143
3. ANALYSIS ON FOODGRAINS (PRIMARY + UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 1.4.2019 | 1890.8495 | 1890.8495 | 0 | 0%
2 | Allocation for 2019-20 | 127621.7672 | 127621.7672 | 0 | 0%
3.2) District-wise opening balance as on 1.4.2019 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation | Opening Stock as on 01.04.2019 | % of OS on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 7781.8184 | 82.1783 | 1.056%
2 | Amreli | 2895.8216 | 36.169 | 1.249%
3 | Anand | 4727.2892 | 79.1226 | 1.674%
4 | Arvalli | 3125.6776 | 67.1954 | 2.15%
5 | Banaskantha | 10990.564 | 62.4411 | 0.5681%
6 | Bharuch | 3103.7572 | 50.1747 | 1.617%
7 | Bhavnagar | 5705.5624 | 59.0302 | 1.035%
8 | Botad | 1831.9908 | 64.976 | 3.547%
9 | Chotta udepur | 3275.8072 | 39.2132 | 1.197%
10 | Dahod | 8471.5744 | 79.2553 | 0.9355%
11 | Dangs | 1242.1204 | 9.527 | 0.767%
12 | Dev bhumi dwarka | 1566.5292 | 81.8945 | 5.228%
13 | Gandhinagar | 3138.3284 | 62.9321 | 2.005%
14 | Gir somnath | 2659.7132 | 80.8827 | 3.041%
15 | Jamnagar | 2465.6656 | 29.5653 | 1.199%
16 | Junagadh | 1422.8904 | 26.7857 | 1.882%
17 | Kheda-Nadiad | 5245.7084 | 40.3922 | 0.77%
18 | Kutch-Bhuj | 5733.466 | 117.191 | 2.044%
19 | Mahisagar | 3651.0312 | 25.9091 | 0.7096%
20 | Mehsana | 5510.0604 | 80.1722 | 1.455%
21 | Morbi | 1972.9268 | 33.8852 | 1.718%
22 | Narmda | 2088.7924 | 46.4513 | 2.224%
23 | Navsari | 1966.944 | 25.533 | 1.298%
24 | Panchmahals | 5805.1716 | 92.2862 | 1.59%
25 | Patan | 4027.8424 | 23.455 | 0.5823%
26 | Porbandar | 1334.8228 | 35.8966 | 2.689%
27 | Rajkot | 3819.4108 | 19.8354 | 0.5193%
28 | Sabarkantha | 4220.0548 | 43.7037 | 1.036%
29 | Surat | 5179.9016 | 117.4947 | 2.268%
30 | Surendranagar | 3071.976 | 60.4005 | 1.966%
31 | Tapi | 2088.0608 | 43.7106 | 2.093%
32 | Vadodara | 3964.0568 | 100.9244 | 2.546%
33 | Valsad | 3536.4304 | 72.2653 | 2.043%
| TOTAL | 127621.7672 | 1890.8495 | 1.482%
3.3) District-wise unspent balance as on 31.03.2020 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2020 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 7781.8184 | 416.1432 | 5.348%
2 | Amreli | 2895.8216 | 172.6608 | 5.962%
3 | Anand | 4727.2892 | 236.9735 | 5.013%
4 | Arvalli | 3125.6776 | 207.4498 | 6.637%
5 | Banaskantha | 10990.564 | 127.9887 | 1.165%
6 | Bharuch | 3103.7572 | 284.5124 | 9.167%
7 | Bhavnagar | 5705.5624 | 288.9143 | 5.064%
8 | Botad | 1831.9908 | 335.7122 | 18.32%
9 | Chotta udepur | 3275.8072 | 5.8286 | 0.1779%
10 | Dahod | 8471.5744 | 106.9552 | 1.263%
11 | Dangs | 1242.1204 | 4.2938 | 0.3457%
12 | Dev bhumi dwarka | 1566.5292 | 123.2979 | 7.871%
13 | Gandhinagar | 3138.3284 | 35.2433 | 1.123%
14 | Gir somnath | 2659.7132 | 205.4674 | 7.725%
15 | Jamnagar | 2465.6656 | 6.6574 | 0.27%
16 | Junagadh | 1422.8904 | 29.6234 | 2.082%
17 | Kheda-Nadiad | 5245.7084 | 11.4488 | 0.2183%
18 | Kutch-Bhuj | 5733.466 | 508.5785 | 8.87%
19 | Mahisagar | 3651.0312 | 292.8721 | 8.022%
20 | Mehsana | 5510.0604 | 262.5203 | 4.764%
21 | Morbi | 1972.9268 | 150.9369 | 7.65%
22 | Narmda | 2088.7924 | 362.7712 | 17.37%
23 | Navsari | 1966.944 | 47.2653 | 2.403%
24 | Panchmahals | 5805.1716 | 351.7988 | 6.06%
25 | Patan | 4027.8424 | 320.5474 | 7.958%
26 | Porbandar | 1334.8228 | -332.2884 | -24.89%
27 | Rajkot | 3819.4108 | 362.3373 | 9.487%
28 | Sabarkantha | 4220.0548 | 88.7883 | 2.104%
29 | Surat | 5179.9016 | 13.3464 | 0.2577%
30 | Surendranagar | 3071.976 | 10.5801 | 0.3444%
31 | Tapi | 2088.0608 | 22.3524 | 1.07%
32 | Vadodara | 3964.0568 | 10.4258 | 0.263%
33 | Valsad | 3536.4304 | 174.988 | 4.948%
| TOTAL | 127621.7672 | 5246.991 | 4.111%
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | Opening balance as on 01.4.19 | Lifting upto 31.03.2020 | Total Availibility | % Availibility
127621.7672 | 1890.8495 | 116965.318 | 118856.1675 | 93.13%
Source: Table AT-6 & 6A of AWP&B 2020-21
3.5) District-wise Foodgrains availability as on 31.03.2020 (Source data: Table AT-6 & 6A of AWP&B 2020-21)
(in MTs)
Sl. No. | District | Allocation | OB as on 01.04.2019 | Lifted from FCI | Total Availibility | % Availibility
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmedabad | 7781.8184 | 82.1783 | 7682.78 | 7764.9583 | 99.78%
2 | Amreli | 2895.8216 | 36.169 | 2747.78 | 2783.949 | 96.14%
3 | Anand | 4727.2892 | 79.1226 | 4599.83 | 4678.9526 | 98.98%
4 | Arvalli | 3125.6776 | 67.1954 | 3103.84 | 3171.0354 | 101.5%
5 | Banaskantha | 10990.564 | 62.4411 | 9114.48 | 9176.9211 | 83.5%
6 | Bharuch | 3103.7572 | 50.1747 | 2915.26 | 2965.4347 | 95.54%
7 | Bhavnagar | 5705.5624 | 59.0302 | 5371.01 | 5430.0402 | 95.17%
8 | Botad | 1831.9908 | 64.976 | 1843.22 | 1908.196 | 104.2%
9 | Chotta udepur | 3275.8072 | 39.2132 | 2491.45 | 2530.6632 | 77.25%
10 | Dahod | 8471.5744 | 79.2553 | 8149.91 | 8229.1653 | 97.14%
11 | Dangs | 1242.1204 | 9.527 | 924.133 | 933.66 | 75.17%
12 | Dev bhumi dwarka | 1566.5292 | 81.8945 | 1521.21 | 1603.1045 | 102.3%
13 | Gandhinagar | 3138.3284 | 62.9321 | 3053.04 | 3115.9721 | 99.29%
14 | Gir somnath | 2659.7132 | 80.8827 | 2571.49 | 2652.3727 | 99.72%
15 | Jamnagar | 2465.6656 | 29.5653 | 1857.27 | 1886.8353 | 76.52%
16 | Junagadh | 1422.8904 | 26.7857 | 1248.383 | 1275.1687 | 89.62%
17 | Kheda-Nadiad | 5245.7084 | 40.3922 | 4670.191 | 4710.5832 | 89.8%
18 | Kutch-Bhuj | 5733.466 | 117.191 | 5714.23 | 5831.421 | 101.7%
19 | Mahisagar | 3651.0312 | 25.9091 | 3553.56 | 3579.4691 | 98.04%
20 | Mehsana | 5510.0604 | 80.1722 | 5313.44 | 5393.6122 | 97.89%
21 | Morbi | 1972.9268 | 33.8852 | 1928.59 | 1962.4752 | 99.47%
22 | Narmda | 2088.7924 | 46.4513 | 2056.62 | 2103.0713 | 100.7%
23 | Navsari | 1966.944 | 25.533 | 1790.218 | 1815.751 | 92.31%
24 | Panchmahals | 5805.1716 | 92.2862 | 5700.09 | 5792.3762 | 99.78%
25 | Patan | 4027.8424 | 23.455 | 3828.03 | 3851.485 | 95.62%
26 | Porbandar | 1334.8228 | 35.8966 | 249.13 | 285.0266 | 21.35%
27 | Rajkot | 3819.4108 | 19.8354 | 3728.62 | 3748.4554 | 98.14%
28 | Sabarkantha | 4220.0548 | 43.7037 | 3709.253 | 3752.9567 | 88.93%
29 | Surat | 5179.9016 | 117.4947 | 4214.7 | 4332.1947 | 83.63%
30 | Surendranagar | 3071.976 | 60.4005 | 2864.8 | 2925.2005 | 95.22%
31 | Tapi | 2088.0608 | 43.7106 | 1812.64 | 1856.3506 | 88.9%
32 | Vadodara | 3964.0568 | 100.9244 | 3390.58 | 3491.5044 | 88.08%
33 | Valsad | 3536.4304 | 72.2653 | 3245.54 | 3317.8053 | 93.82%
| TOTAL | 127621.7672 | 1890.8495 | 116965.318 | 118856.1675 | 93.13%
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | T. Availibility | % T. Availibility | Utilisation | % Utilisation
127621.7672 | 118856.1675 | 93.13% | 113609.1765 | 89.02%
3.7) District-wise Utilisation of foodgrains (Source data: Table AT-6 & 6A of AWP&B 2020-21)
Sl. No. | District | Allocation | Utilisation | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 7781.8184 | 7348.8151 | 94.44%
2 | Amreli | 2895.8216 | 2611.2883 | 90.17%
3 | Anand | 4727.2892 | 4441.9791 | 93.96%
4 | Arvalli | 3125.6776 | 2963.5856 | 94.81%
5 | Banaskantha | 10990.564 | 9048.9324 | 82.33%
6 | Bharuch | 3103.7572 | 2680.9223 | 86.38%
7 | Bhavnagar | 5705.5624 | 5141.1259 | 90.11%
8 | Botad | 1831.9908 | 1572.4838 | 85.83%
9 | Chotta udepur | 3275.8072 | 2524.8345 | 77.08%
10 | Dahod | 8471.5744 | 8122.2101 | 95.88%
11 | Dangs | 1242.1204 | 929.3662 | 74.82%
12 | Dev bhumi dwarka | 1566.5292 | 1479.8066 | 94.46%
13 | Gandhinagar | 3138.3284 | 3080.7289 | 98.16%
14 | Gir somnath | 2659.7132 | 2446.9053 | 92%
15 | Jamnagar | 2465.6656 | 1880.1779 | 76.25%
16 | Junagadh | 1422.8904 | 1245.5453 | 87.54%
17 | Kheda-Nadiad | 5245.7084 | 4699.1343 | 89.58%
18 | Kutch-Bhuj | 5733.466 | 5322.8425 | 92.84%
19 | Mahisagar | 3651.0312 | 3286.597 | 90.02%
20 | Mehsana | 5510.0604 | 5131.0919 | 93.12%
21 | Morbi | 1972.9268 | 1811.5382 | 91.82%
22 | Narmda | 2088.7924 | 1740.3001 | 83.32%
23 | Navsari | 1966.944 | 1768.4857 | 89.91%
24 | Panchmahals | 5805.1716 | 5440.5773 | 93.72%
25 | Patan | 4027.8424 | 3530.9376 | 87.66%
26 | Porbandar | 1334.8228 | 617.315 | 46.25%
27 | Rajkot | 3819.4108 | 3386.118 | 88.66%
28 | Sabarkantha | 4220.0548 | 3664.1684 | 86.83%
29 | Surat | 5179.9016 | 4318.8484 | 83.38%
30 | Surendranagar | 3071.976 | 2914.6204 | 94.88%
31 | Tapi | 2088.0608 | 1833.9982 | 87.83%
32 | Vadodara | 3964.0568 | 3481.0787 | 87.82%
33 | Valsad | 3536.4304 | 3142.8173 | 88.87%
| TOTAL | 127621.7672 | 113609.1765 | 89.02%
3.8) Cost of Foodgrains, Payment to FCI
Allocation | Bills submited by FCI | Payment made to FCI | % payment
3144.43 | 2928.1851 | 2891.6124 | 98.75%
3.9) Payment of cost of foodgrain to FCI
Sl. No. | District | Allocation | Bills raised by FCI | Payment to FCI | Pending Bills | % Bill paid
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmedabad | 208.9158 | 192.1186 | 192.1186 | 0 | 100%
2 | Amreli | 74.7206 | 68.7129 | 68.7129 | 0 | 100%
3 | Anand | 125.0824 | 115.0256 | 115.0256 | 0 | 100%
4 | Arvalli | 84.4022 | 77.6161 | 77.6161 | 0 | 100%
5 | Banaskantha | 220.5746 | 227.9318 | 202.84 | 25.0918 | 88.99%
6 | Bharuch | 79.2536 | 72.8815 | 72.8815 | 0 | 100%
7 | Bhavnagar | 146.0541 | 134.3111 | 134.3111 | 0 | 100%
8 | Botad | 50.1223 | 46.0924 | 46.0924 | 0 | 100%
9 | Chotta udepur | 68.0568 | 62.5849 | 62.5849 | 0 | 100%
10 | Dahod | 221.6216 | 203.8028 | 203.8028 | 0 | 100%
11 | Dangs | 25.3567 | 23.318 | 23.318 | 0 | 100%
12 | Dev bhumi dwarka | 41.3661 | 38.0402 | 38.0402 | 0 | 100%
13 | Gandhinagar | 83.0209 | 76.3459 | 76.3459 | 0 | 100%
14 | Gir somnath | 69.9261 | 64.3039 | 64.3039 | 0 | 100%
15 | Jamnagar | 50.5035 | 46.4429 | 46.4429 | 0 | 100%
16 | Junagadh | 33.9339 | 31.2056 | 31.2056 | 0 | 100%
17 | Kheda-Nadiad | 155.3848 | 142.8916 | 142.8916 | 0 | 100%
18 | Kutch-Bhuj | 127.5614 | 117.3052 | 117.3052 | 0 | 100%
19 | Mahisagar | 96.6315 | 88.8622 | 88.8622 | 0 | 100%
20 | Mehsana | 144.488 | 132.8709 | 132.8709 | 0 | 100%
21 | Morbi | 52.4446 | 48.228 | 48.228 | 0 | 100%
22 | Narmda | 55.9253 | 51.4288 | 51.4288 | 0 | 100%
23 | Navsari | 48.6938 | 44.7788 | 44.7788 | 0 | 100%
24 | Panchmahals | 155.0014 | 142.539 | 142.539 | 0 | 100%
25 | Patan | 104.0957 | 95.7262 | 95.7262 | 0 | 100%
26 | Porbandar | 7.3097 | 6.722 | 6.722 | 0 | 100%
27 | Rajkot | 101.3918 | 93.2397 | 93.2397 | 0 | 100%
28 | Sabarkantha | 89.9088 | 94.1609 | 82.68 | 11.4809 | 87.81%
29 | Surat | 114.5273 | 105.3191 | 105.3191 | 0 | 100%
30 | Surendranagar | 77.9031 | 71.6396 | 71.6396 | 0 | 100%
31 | Tapi | 49.7987 | 45.7948 | 45.7948 | 0 | 100%
32 | Vadodara | 92.1959 | 84.7832 | 84.7832 | 0 | 100%
33 | Valsad | 88.257 | 81.161 | 81.161 | 0 | 100%
| TOTAL | 3144.43 | 2928.1851 | 2891.6124 | 36.5727 | 98.75%
4. ANALYSIS ON COOKING COST (PRIMARY + UPPER PRIMARY)
4.1) ANALYSIS ON OPENING BALANACE AND CLOSING BALANACE
4.1.1) District-wise opening balance as on 01.04.2019 (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | % of OB on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 4558.1616 | 1114.699 | 24.46%
2 | Amreli | 1008.7705 | 246.0454 | 24.39%
3 | Anand | 2099.2817 | 513.1708 | 24.45%
4 | Arvalli | 1243.4707 | 304.0061 | 24.45%
5 | Banaskantha | 5920.3134 | 1447.7869 | 24.45%
6 | Bharuch | 1104.6716 | 269.9668 | 24.44%
7 | Bhavnagar | 2199.5404 | 538.0168 | 24.46%
8 | Botad | 620.43 | 152.0245 | 24.5%
9 | Chotta udepur | 1201.4953 | 294.1352 | 24.48%
10 | Dahod | 3390.4917 | 828.6197 | 24.44%
11 | Dangs | 447.074 | 109.3444 | 24.46%
12 | Dev bhumi dwarka | 516.8915 | 126.3449 | 24.44%
13 | Gandhinagar | 2298.3976 | 561.6043 | 24.43%
14 | Gir somnath | 933.0868 | 228.5335 | 24.49%
15 | Jamnagar | 859.8769 | 210.1876 | 24.44%
16 | Junagadh | 676.2051 | 165.9145 | 24.54%
17 | Kheda-Nadiad | 2053.3987 | 502.6085 | 24.48%
18 | Kutch-Bhuj | 2230.3908 | 545.5737 | 24.46%
19 | Mahisagar | 1518.0248 | 371.2568 | 24.46%
20 | Mehsana | 1643.815 | 402.4863 | 24.48%
21 | Morbi | 770.8977 | 188.3089 | 24.43%
22 | Narmda | 762.2462 | 186.7743 | 24.5%
23 | Navsari | 1282.6484 | 313.3269 | 24.43%
24 | Panchmahals | 1935.0151 | 473.7226 | 24.48%
25 | Patan | 1453.4787 | 356.0159 | 24.49%
26 | Porbandar | 283.6946 | 69.3918 | 24.46%
27 | Rajkot | 1721.3574 | 421.5726 | 24.49%
28 | Sabarkantha | 1546.2986 | 379.0363 | 24.51%
29 | Surat | 4417.7781 | 1081.3823 | 24.48%
30 | Surendranagar | 1340.7045 | 327.6307 | 24.44%
31 | Tapi | 769.9593 | 188.2705 | 24.45%
32 | Vadodara | 2712.3454 | 663.5507 | 24.46%
33 | Valsad | 1661.8713 | 407.741 | 24.54%
| TOTAL | 57182.0833 | 13989.05 | 24.46%
4.1.2) District-wise unspent balance as on 31.03.2020 Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Unspent Balance as on 31.03.2020 | % of UB on allocation
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 4558.1616 | 1623.0355 | 35.61%
2 | Amreli | 1008.7705 | 343.781 | 34.08%
3 | Anand | 2099.2817 | 732.0952 | 34.87%
4 | Arvalli | 1243.4707 | 442.7381 | 35.61%
5 | Banaskantha | 5920.3134 | 2093.6053 | 35.36%
6 | Bharuch | 1104.6716 | 379.7615 | 34.38%
7 | Bhavnagar | 2199.5404 | 784.4577 | 35.66%
8 | Botad | 620.43 | 223.6871 | 36.05%
9 | Chotta udepur | 1201.4953 | 423.0666 | 35.21%
10 | Dahod | 3390.4917 | 1194.8148 | 35.24%
11 | Dangs | 447.074 | 155.9275 | 34.88%
12 | Dev bhumi dwarka | 516.8915 | 180.4015 | 34.9%
13 | Gandhinagar | 2298.3976 | 833.212 | 36.25%
14 | Gir somnath | 933.0868 | 345.1551 | 36.99%
15 | Jamnagar | 859.8769 | 304.1745 | 35.37%
16 | Junagadh | 676.2051 | 243.2567 | 35.97%
17 | Kheda-Nadiad | 2053.3987 | 713.7848 | 34.76%
18 | Kutch-Bhuj | 2230.3908 | 797.447 | 35.75%
19 | Mahisagar | 1518.0248 | 539.8698 | 35.56%
20 | Mehsana | 1643.815 | 607.007 | 36.93%
21 | Morbi | 770.8977 | 262.9371 | 34.11%
22 | Narmda | 762.2462 | 275.0533 | 36.08%
23 | Navsari | 1282.6484 | 454.2735 | 35.42%
24 | Panchmahals | 1935.0151 | 683.1634 | 35.31%
25 | Patan | 1453.4787 | 514.8446 | 35.42%
26 | Porbandar | 283.6946 | 99.8926 | 35.21%
27 | Rajkot | 1721.3574 | 629.3294 | 36.56%
28 | Sabarkantha | 1546.2986 | 584.0464 | 37.77%
29 | Surat | 4417.7781 | 1565.8081 | 35.44%
30 | Surendranagar | 1340.7045 | 467.2034 | 34.85%
31 | Tapi | 769.9593 | 270.8347 | 35.18%
32 | Vadodara | 2712.3454 | 965.3926 | 35.59%
33 | Valsad | 1661.8713 | 590.3158 | 35.52%
| TOTAL | 57182.0833 | 20324.3736 | 35.54%
4.2) Cooking cost allocation and disbursed to Districts
(Rs. In lakh)
Allocation | OB as on 01.4.19 | Disbursed to Dist | Total Availibility | % Availibility
57182.0833 | 13989.05 | 43561.75 | 57550.8 | 100.6%
4.3) District-wise Cooking Cost availability (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | Cooking assistance received | Total Availibility of cooking cost | % Availibility of cooking cost
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmedabad | 4558.1616 | 1114.699 | 3472.587 | 4587.286 | 100.6%
2 | Amreli | 1008.7705 | 246.0454 | 767.1789 | 1013.2243 | 100.4%
3 | Anand | 2099.2817 | 513.1708 | 1597.9291 | 2111.1 | 100.6%
4 | Arvalli | 1243.4707 | 304.0061 | 947.4665 | 1251.4726 | 100.6%
5 | Banaskantha | 5920.3134 | 1447.7869 | 4509.4199 | 5957.2068 | 100.6%
6 | Bharuch | 1104.6716 | 269.9668 | 840.2731 | 1110.2399 | 100.5%
7 | Bhavnagar | 2199.5404 | 538.0168 | 1676.0462 | 2214.0629 | 100.7%
8 | Botad | 620.43 | 152.0245 | 472.7184 | 624.7428 | 100.7%
9 | Chotta udepur | 1201.4953 | 294.1352 | 914.6533 | 1208.7885 | 100.6%
10 | Dahod | 3390.4917 | 828.6197 | 2582.1482 | 3410.7679 | 100.6%
11 | Dangs | 447.074 | 109.3444 | 340.3061 | 449.6506 | 100.6%
12 | Dev bhumi dwarka | 516.8915 | 126.3449 | 393.4634 | 519.8083 | 100.6%
13 | Gandhinagar | 2298.3976 | 561.6043 | 1751.778 | 2313.3823 | 100.7%
14 | Gir somnath | 933.0868 | 228.5335 | 712.2958 | 940.8293 | 100.8%
15 | Jamnagar | 859.8769 | 210.1876 | 654.9853 | 865.1729 | 100.6%
16 | Junagadh | 676.2051 | 165.9145 | 515.4786 | 681.393 | 100.8%
17 | Kheda-Nadiad | 2053.3987 | 502.6085 | 1562.4603 | 2065.0688 | 100.6%
18 | Kutch-Bhuj | 2230.3908 | 545.5737 | 1699.7634 | 2245.337 | 100.7%
19 | Mahisagar | 1518.0248 | 371.2568 | 1156.3893 | 1527.6461 | 100.6%
20 | Mehsana | 1643.815 | 402.4863 | 1254.7334 | 1657.2197 | 100.8%
21 | Morbi | 770.8977 | 188.3089 | 586.1887 | 774.4977 | 100.5%
22 | Narmda | 762.2462 | 186.7743 | 581.3262 | 768.1005 | 100.8%
23 | Navsari | 1282.6484 | 313.3269 | 977.1079 | 1290.4348 | 100.6%
24 | Panchmahals | 1935.0151 | 473.7226 | 1473.6442 | 1947.3669 | 100.6%
25 | Patan | 1453.4787 | 356.0159 | 1107.0398 | 1463.0556 | 100.7%
26 | Porbandar | 283.6946 | 69.3918 | 216.1508 | 285.5426 | 100.7%
27 | Rajkot | 1721.3574 | 421.5726 | 1313.2826 | 1734.8551 | 100.8%
28 | Sabarkantha | 1546.2986 | 379.0363 | 1180.4261 | 1559.4624 | 100.9%
29 | Surat | 4417.7781 | 1081.3823 | 3365.1758 | 4446.558 | 100.7%
30 | Surendranagar | 1340.7045 | 327.6307 | 1020.507 | 1348.1377 | 100.6%
31 | Tapi | 769.9593 | 188.2705 | 586.3244 | 774.5949 | 100.6%
32 | Vadodara | 2712.3454 | 663.5507 | 2066.6657 | 2730.2164 | 100.7%
33 | Valsad | 1661.8713 | 407.741 | 1265.8368 | 1673.5777 | 100.7%
| TOTAL | 57182.0833 | 13989.05 | 43561.75 | 57550.8 | 100.6%
4.4) Cooking Cost Utilisation |  |  |  | (Rs. In lakh)
Allocation | Total available | % available | Utilisation | % Utilisation
57182.0833 | 57550.8 | 100.6% | 37226.4264 | 65.1%
4.5) District-wise Utilisation of Cooking cost (Source data: Table AT-7 & 7A of AWP&B 2020-21)
(Rs. In lakh)
S.No. | Name of District | Allocation | Utilisation of Cooking assistance | % Utilisation
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 4558.1616 | 2964.2505 | 65.03%
2 | Amreli | 1008.7705 | 669.4433 | 66.36%
3 | Anand | 2099.2817 | 1379.0047 | 65.69%
4 | Arvalli | 1243.4707 | 808.7346 | 65.04%
5 | Banaskantha | 5920.3134 | 3863.6015 | 65.26%
6 | Bharuch | 1104.6716 | 730.4784 | 66.13%
7 | Bhavnagar | 2199.5404 | 1429.6053 | 65%
8 | Botad | 620.43 | 401.0557 | 64.64%
9 | Chotta udepur | 1201.4953 | 785.7219 | 65.4%
10 | Dahod | 3390.4917 | 2215.9531 | 65.36%
11 | Dangs | 447.074 | 293.7231 | 65.7%
12 | Dev bhumi dwarka | 516.8915 | 339.4068 | 65.66%
13 | Gandhinagar | 2298.3976 | 1480.1703 | 64.4%
14 | Gir somnath | 933.0868 | 595.6742 | 63.84%
15 | Jamnagar | 859.8769 | 560.9984 | 65.24%
16 | Junagadh | 676.2051 | 438.1363 | 64.79%
17 | Kheda-Nadiad | 2053.3987 | 1351.284 | 65.81%
18 | Kutch-Bhuj | 2230.3908 | 1447.89 | 64.92%
19 | Mahisagar | 1518.0248 | 987.7763 | 65.07%
20 | Mehsana | 1643.815 | 1050.2126 | 63.89%
21 | Morbi | 770.8977 | 511.5606 | 66.36%
22 | Narmda | 762.2462 | 493.0472 | 64.68%
23 | Navsari | 1282.6484 | 836.1613 | 65.19%
24 | Panchmahals | 1935.0151 | 1264.2035 | 65.33%
25 | Patan | 1453.4787 | 948.211 | 65.24%
26 | Porbandar | 283.6946 | 185.65 | 65.44%
27 | Rajkot | 1721.3574 | 1105.5257 | 64.22%
28 | Sabarkantha | 1546.2986 | 975.416 | 63.08%
29 | Surat | 4417.7781 | 2880.7499 | 65.21%
30 | Surendranagar | 1340.7045 | 880.9343 | 65.71%
31 | Tapi | 769.9593 | 503.7602 | 65.43%
32 | Vadodara | 2712.3454 | 1764.8238 | 65.07%
33 | Valsad | 1661.8713 | 1083.2619 | 65.18%
| TOTAL | 57182.0833 | 37226.4264 | 65.1%
5. Reconciliation of Utilisation and Performance during 2019-20 [PRIMARY+ UPPER PRIMARY]
5.1 Reconciliation between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.7 and 4.5 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | 2 | 3 | 4 | 5
1 | Ahmedabad | 94.44% | 65.03% | -29.4%
2 | Amreli | 90.17% | 66.36% | -23.81%
3 | Anand | 93.96% | 65.69% | -28.28%
4 | Arvalli | 94.81% | 65.04% | -29.78%
5 | Banaskantha | 82.33% | 65.26% | -17.07%
6 | Bharuch | 86.38% | 66.13% | -20.25%
7 | Bhavnagar | 90.11% | 65% | -25.11%
8 | Botad | 85.83% | 64.64% | -21.19%
9 | Chotta udepur | 77.08% | 65.4% | -11.68%
10 | Dahod | 95.88% | 65.36% | -30.52%
11 | Dangs | 74.82% | 65.7% | -9.122%
12 | Dev bhumi dwarka | 94.46% | 65.66% | -28.8%
13 | Gandhinagar | 98.16% | 64.4% | -33.76%
14 | Gir somnath | 92% | 63.84% | -28.16%
15 | Jamnagar | 76.25% | 65.24% | -11.01%
16 | Junagadh | 87.54% | 64.79% | -22.74%
17 | Kheda-Nadiad | 89.58% | 65.81% | -23.77%
18 | Kutch-Bhuj | 92.84% | 64.92% | -27.92%
19 | Mahisagar | 90.02% | 65.07% | -24.95%
20 | Mehsana | 93.12% | 63.89% | -29.23%
21 | Morbi | 91.82% | 66.36% | -25.46%
22 | Narmda | 83.32% | 64.68% | -18.63%
23 | Navsari | 89.91% | 65.19% | -24.72%
24 | Panchmahals | 93.72% | 65.33% | -28.39%
25 | Patan | 87.66% | 65.24% | -22.43%
26 | Porbandar | 46.25% | 65.44% | 19.19%
27 | Rajkot | 88.66% | 64.22% | -24.43%
28 | Sabarkantha | 86.83% | 63.08% | -23.75%
29 | Surat | 83.38% | 65.21% | -18.17%
30 | Surendranagar | 94.88% | 65.71% | -29.17%
31 | Tapi | 87.83% | 65.43% | -22.41%
32 | Vadodara | 87.82% | 65.07% | -22.75%
33 | Valsad | 88.87% | 65.18% | -23.69%
| TOTAL | 89.02% | 65.1% | -23.92%
5.2 Reconciliation of Food grains utilisation during 2019-20 (Source data: para 2.7 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 2019-20 | Expected consumption of food grains | Actual consumption of food grains | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmedabad | 56087559 | 6737.4302 | 7348.8151 | 109.1%
2 | Amreli | 20481012 | 2448.6138 | 2611.2883 | 106.6%
3 | Anand | 35259543 | 4151.9223 | 4441.9791 | 107%
4 | Arvalli | 24262578 | 2838.24 | 2963.5856 | 104.4%
5 | Banaskantha | 81583605 | 9549.4018 | 9048.9324 | 94.76%
6 | Bharuch | 22156497 | 2605.203 | 2680.9223 | 102.9%
7 | Bhavnagar | 40170087 | 4816.989 | 5141.1259 | 106.7%
8 | Botad | 11576277 | 1374.894 | 1572.4838 | 114.4%
9 | Chotta udepur | 26166726 | 3016.2618 | 2524.8345 | 83.71%
10 | Dahod | 71667504 | 8351.5941 | 8122.2101 | 97.25%
11 | Dangs | 8975934 | 1041.7288 | 929.3662 | 89.21%
12 | Dev bhumi dwarka | 12595176 | 1500.5615 | 1479.8066 | 98.62%
13 | Gandhinagar | 25814619 | 3161.1748 | 3080.7289 | 97.46%
14 | Gir somnath | 19429794 | 2369.4322 | 2446.9053 | 103.3%
15 | Jamnagar | 20489274 | 2425.8204 | 1880.1779 | 77.51%
16 | Junagadh | 10845333 | 1299.1266 | 1245.5453 | 95.88%
17 | Kheda-Nadiad | 44198055 | 5266.454 | 4699.1343 | 89.23%
18 | Kutch-Bhuj | 41773644 | 4915.3432 | 5322.8425 | 108.3%
19 | Mahisagar | 27577098 | 3242.677 | 3286.597 | 101.4%
20 | Mehsana | 32710716 | 3959.5635 | 5131.0919 | 129.6%
21 | Morbi | 15478857 | 1814.323 | 1811.5382 | 99.85%
22 | Narmda | 14103963 | 1644.4417 | 1740.3001 | 105.8%
23 | Navsari | 14755932 | 1771.5793 | 1768.4857 | 99.83%
24 | Panchmahals | 45631998 | 5392.6439 | 5440.5773 | 100.9%
25 | Patan | 27913410 | 3341.7603 | 3530.9376 | 105.7%
26 | Porbandar | 6982605 | 850.6093 | 617.315 | 72.57%
27 | Rajkot | 28548612 | 3371.5885 | 3386.118 | 100.4%
28 | Sabarkantha | 33711633 | 3967.4003 | 3664.1684 | 92.36%
29 | Surat | 47438460 | 5660.9037 | 4318.8484 | 76.29%
30 | Surendranagar | 27406026 | 3276.5391 | 2914.6204 | 88.95%
31 | Tapi | 16692399 | 1948.8721 | 1833.9982 | 94.11%
32 | Vadodara | 32384124 | 3819.9478 | 3481.0787 | 91.13%
33 | Valsad | 26554554 | 3115.6974 | 3142.8173 | 100.9%
| TOTAL | 971423604 | 115048.7388 | 113609.1765 | 98.75%
5.3 Reconciliation of Cooking Cost utilisation during 2019-20 (Source data: para 2.5 and 4.7 above)
(Rs. in Lakh)
Sr. No. | District | No. of Meals served during 2019-20 | Expected expenditure of cooking cost | Actual expenditure of cooking cost | % consumption
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmedabad | 56087559 | 3016.1114 | 2964.2505 | 98.28%
2 | Amreli | 20481012 | 1096.178 | 669.4433 | 61.07%
3 | Anand | 35259543 | 1858.8093 | 1379.0047 | 74.19%
4 | Arvalli | 24262578 | 1270.7076 | 808.7346 | 63.64%
5 | Banaskantha | 81583605 | 4275.3499 | 3863.6015 | 90.37%
6 | Bharuch | 22156497 | 1166.3518 | 730.4784 | 62.63%
7 | Bhavnagar | 40170087 | 2156.4111 | 1429.6053 | 66.3%
8 | Botad | 11576277 | 615.518 | 401.0557 | 65.16%
9 | Chotta udepur | 26166726 | 1350.4861 | 785.7219 | 58.18%
10 | Dahod | 71667504 | 3739.1445 | 2215.9531 | 59.26%
11 | Dangs | 8975934 | 466.4063 | 293.7231 | 62.98%
12 | Dev bhumi dwarka | 12595176 | 671.7694 | 339.4068 | 50.52%
13 | Gandhinagar | 25814619 | 1415.0469 | 1480.1703 | 104.6%
14 | Gir somnath | 19429794 | 1060.6527 | 595.6742 | 56.16%
15 | Jamnagar | 20489274 | 1086.0138 | 560.9984 | 51.66%
16 | Junagadh | 10845333 | 581.5795 | 438.1363 | 75.34%
17 | Kheda-Nadiad | 44198055 | 2357.6781 | 1351.284 | 57.31%
18 | Kutch-Bhuj | 41773644 | 2200.5978 | 1447.89 | 65.8%
19 | Mahisagar | 27577098 | 1451.7494 | 987.7763 | 68.04%
20 | Mehsana | 32710716 | 1772.5075 | 1050.2126 | 59.25%
21 | Morbi | 15478857 | 812.2839 | 511.5606 | 62.98%
22 | Narmda | 14103963 | 736.2418 | 493.0472 | 66.97%
23 | Navsari | 14755932 | 793.0756 | 836.1613 | 105.4%
24 | Panchmahals | 45631998 | 2414.2456 | 1264.2035 | 52.36%
25 | Patan | 27913410 | 1496.0078 | 948.211 | 63.38%
26 | Porbandar | 6982605 | 380.7683 | 185.65 | 48.76%
27 | Rajkot | 28548612 | 1509.4382 | 1105.5257 | 73.24%
28 | Sabarkantha | 33711633 | 1776.2028 | 975.416 | 54.92%
29 | Surat | 47438460 | 2534.2507 | 2880.7499 | 113.7%
30 | Surendranagar | 27406026 | 1466.8176 | 880.9343 | 60.06%
31 | Tapi | 16692399 | 872.5355 | 503.7602 | 57.74%
32 | Vadodara | 32384124 | 1710.1736 | 1764.8238 | 103.2%
33 | Valsad | 26554554 | 1394.912 | 1083.2619 | 77.66%
| TOTAL | 971423604 | 51506.0222 | 37226.4264 | 72.28%
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
6.1) District-wise number of cook-cum-Helpers approved by PAB and engaged by State
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | PAB Approval | Engaged by State | Not engaged
1 | 2 | 3 | 4 | 5 = (4 - 3)
1 | Ahmedabad | 3699 | 3699 | 0
2 | Amreli | 2377 | 2377 | 0
3 | Anand | 3445 | 3445 | 0
4 | Arvalli | 3556 | 3556 | 0
5 | Banaskantha | 7608 | 7608 | 0
6 | Bharuch | 2923 | 2923 | 0
7 | Bhavnagar | 3051 | 3051 | 0
8 | Botad | 873 | 873 | 0
9 | Chotta udepur | 3776 | 3776 | 0
10 | Dahod | 5470 | 5470 | 0
11 | Dangs | 1221 | 1221 | 0
12 | Dev bhumi dwarka | 1960 | 1960 | 0
13 | Gandhinagar | 1165 | 1165 | 0
14 | Gir somnath | 1794 | 1794 | 0
15 | Jamnagar | 2045 | 2045 | 0
16 | Junagadh | 2183 | 2183 | 0
17 | Kheda-Nadiad | 5272 | 5272 | 0
18 | Kutch-Bhuj | 4390 | 4390 | 0
19 | Mahisagar | 3209 | 3209 | 0
20 | Mehsana | 3361 | 3361 | 0
21 | Morbi | 1635 | 1635 | 0
22 | Narmda | 2070 | 2070 | 0
23 | Navsari | 800 | 800 | 0
24 | Panchmahals | 3993 | 3993 | 0
25 | Patan | 2541 | 2541 | 0
26 | Porbandar | 950 | 950 | 0
27 | Rajkot | 2650 | 2650 | 0
28 | Sabarkantha | 3732 | 3732 | 0
29 | Surat | 4149 | 4149 | 0
30 | Surendranagar | 2645 | 2645 | 0
31 | Tapi | 2564 | 2564 | 0
32 | Vadodara | 2899 | 2899 | 0
33 | Valsad | 2323 | 2323 | 0
| TOTAL | 96329 | 96329 | 0
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | Allocation | Opening Balance as on 01.04.2019 | Amount released | Total availability | % Availibilty |  |  | 84.2187
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Ahmedabad | 362.864 | 26.1747 | 329.8684 | 356.0431 | 98.12%
2 | Amreli | 290.7775 | 20.8422 | 264.3367 | 285.1789 | 98.07%
3 | Anand | 325.9111 | 24.0207 | 296.2756 | 320.2963 | 98.28%
4 | Arvalli | 328.6386 | 22.8288 | 298.7551 | 321.5839 | 97.85%
5 | Banaskantha | 752.3778 | 53.8087 | 683.9632 | 737.7719 | 98.06%
6 | Bharuch | 275.498 | 22.4511 | 250.4466 | 272.8977 | 99.06%
7 | Bhavnagar | 298.3205 | 18.0836 | 271.1939 | 289.2775 | 96.97%
8 | Botad | 87.7346 | 4.9791 | 79.7568 | 84.736 | 96.58%
9 | Chotta udepur | 361.1354 | 19.2186 | 328.2969 | 347.5156 | 96.23%
10 | Dahod | 607.8083 | 28.4049 | 552.5396 | 580.9445 | 95.58%
11 | Dangs | 141.6021 | 7.1142 | 128.7261 | 135.8402 | 95.93%
12 | Dev bhumi dwarka | 143.4384 | 6.3636 | 130.3954 | 136.7591 | 95.34%
13 | Gandhinagar | 205.5269 | 15.4406 | 186.8382 | 202.2788 | 98.42%
14 | Gir somnath | 173.2155 | 10.8279 | 157.4649 | 168.2928 | 97.16%
15 | Jamnagar | 164.5109 | 11.3792 | 149.5518 | 160.931 | 97.82%
16 | Junagadh | 168.6426 | 13.8451 | 153.3078 | 167.1528 | 99.12%
17 | Kheda-Nadiad | 411.1559 | 26.9526 | 373.7691 | 400.7216 | 97.46%
18 | Kutch-Bhuj | 485.4717 | 27.5769 | 441.3272 | 468.9041 | 96.59%
19 | Mahisagar | 280.7802 | 23.5226 | 255.2486 | 278.7712 | 99.28%
20 | Mehsana | 353.3635 | 19.1048 | 321.2317 | 340.3366 | 96.31%
21 | Morbi | 138.0325 | 8.9022 | 125.481 | 134.3833 | 97.36%
22 | Narmda | 179.945 | 12.7476 | 163.5824 | 176.33 | 97.99%
23 | Navsari | 85.6916 | 7.6867 | 77.8996 | 85.5863 | 99.88%
24 | Panchmahals | 460.8415 | 24.5746 | 418.9368 | 443.5114 | 96.24%
25 | Patan | 253.8785 | 14.4336 | 230.7931 | 245.2267 | 96.59%
26 | Porbandar | 76.8935 | 5.1021 | 69.9015 | 75.0036 | 97.54%
27 | Rajkot | 297.7442 | 22.4348 | 270.67 | 293.1048 | 98.44%
28 | Sabarkantha | 413.4498 | 27.2224 | 375.8544 | 403.0768 | 97.49%
29 | Surat | 409.8797 | 21.6607 | 372.6089 | 394.2696 | 96.19%
30 | Surendranagar | 352.1304 | 15.6274 | 320.1108 | 335.7381 | 95.34%
31 | Tapi | 233.2444 | 12.6656 | 212.0352 | 224.7008 | 96.34%
32 | Vadodara | 289.1512 | 20.6357 | 262.8584 | 283.4941 | 98.04%
33 | Valsad | 223.244 | 10.4369 | 202.9442 | 213.3811 | 95.58%
| TOTAL | 9632.9 | 607.07 | 8756.97 | 9364.04 | 97.21%
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | Allocation | Total Availability | Payment of hon. to CCH | % payment to CCH against allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmedabad | 362.864 | 356.0431 | 357.2355 | 98.45%
2 | Amreli | 290.7775 | 285.1789 | 286.7567 | 98.62%
3 | Anand | 325.9111 | 320.2963 | 321.0401 | 98.51%
4 | Arvalli | 328.6386 | 321.5839 | 323.8083 | 98.53%
5 | Banaskantha | 752.3778 | 737.7719 | 740.707 | 98.45%
6 | Bharuch | 275.498 | 272.8977 | 271.1085 | 98.41%
7 | Bhavnagar | 298.3205 | 289.2775 | 294.0242 | 98.56%
8 | Botad | 87.7346 | 84.736 | 86.3734 | 98.45%
9 | Chotta udepur | 361.1354 | 347.5156 | 356.4002 | 98.69%
10 | Dahod | 607.8083 | 580.9445 | 598.4685 | 98.46%
11 | Dangs | 141.6021 | 135.8402 | 139.5213 | 98.53%
12 | Dev bhumi dwarka | 143.4384 | 136.7591 | 141.2819 | 98.5%
13 | Gandhinagar | 205.5269 | 202.2788 | 205.8328 | 100.1%
14 | Gir somnath | 173.2155 | 168.2928 | 173.4272 | 100.1%
15 | Jamnagar | 164.5109 | 160.931 | 161.9636 | 98.45%
16 | Junagadh | 168.6426 | 167.1528 | 166.0074 | 98.44%
17 | Kheda-Nadiad | 411.1559 | 400.7216 | 405.06 | 98.52%
18 | Kutch-Bhuj | 485.4717 | 468.9041 | 478.3247 | 98.53%
19 | Mahisagar | 280.7802 | 278.7712 | 276.2511 | 98.39%
20 | Mehsana | 353.3635 | 340.3366 | 347.8609 | 98.44%
21 | Morbi | 138.0325 | 134.3833 | 135.88 | 98.44%
22 | Narmda | 179.945 | 176.33 | 177.552 | 98.67%
23 | Navsari | 85.6916 | 85.5863 | 84.3532 | 98.44%
24 | Panchmahals | 460.8415 | 443.5114 | 461.1247 | 100.1%
25 | Patan | 253.8785 | 245.2267 | 250.8593 | 98.81%
26 | Porbandar | 76.8935 | 75.0036 | 75.616 | 98.34%
27 | Rajkot | 297.7442 | 293.1048 | 293.0313 | 98.42%
28 | Sabarkantha | 413.4498 | 403.0768 | 406.8166 | 98.4%
29 | Surat | 409.8797 | 394.2696 | 405.243 | 98.87%
30 | Surendranagar | 352.1304 | 335.7381 | 343.8994 | 97.66%
31 | Tapi | 233.2444 | 224.7008 | 229.6267 | 98.45%
32 | Vadodara | 289.1512 | 283.4941 | 284.7183 | 98.47%
33 | Valsad | 223.244 | 213.3811 | 219.7744 | 98.45%
| TOTAL | 9632.9 | 9364.04 | 9499.9479 | 98.62%
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
(Refer table AT_8 and AT-8A, AWP&B, 2020-21)
S.No. | Name of District | Allocation | Total Availability | Unspent balance as on 31.03.2020 | % of UB as on Allocation
1 | 2 | 3 | 4 | 5 | 6
1 | Ahmedabad | 362.864 | 356.0431 | -1.1924 | -0.3286%
2 | Amreli | 290.7775 | 285.1789 | -1.5778 | -0.5426%
3 | Anand | 325.9111 | 320.2963 | -0.74373 | -0.2282%
4 | Arvalli | 328.6386 | 321.5839 | -2.2244 | -0.6769%
5 | Banaskantha | 752.3778 | 737.7719 | -2.9351 | -0.3901%
6 | Bharuch | 275.498 | 272.8977 | 1.7893 | 0.6495%
7 | Bhavnagar | 298.3205 | 289.2775 | -4.7467 | -1.591%
8 | Botad | 87.7346 | 84.736 | -1.6375 | -1.866%
9 | Chotta udepur | 361.1354 | 347.5156 | -8.8846 | -2.46%
10 | Dahod | 607.8083 | 580.9445 | -17.524 | -2.883%
11 | Dangs | 141.6021 | 135.8402 | -3.6811 | -2.6%
12 | Dev bhumi dwarka | 143.4384 | 136.7591 | -4.5228 | -3.153%
13 | Gandhinagar | 205.5269 | 202.2788 | -3.554 | -1.729%
14 | Gir somnath | 173.2155 | 168.2928 | -5.1345 | -2.964%
15 | Jamnagar | 164.5109 | 160.931 | -1.0327 | -0.6277%
16 | Junagadh | 168.6426 | 167.1528 | 1.1454 | 0.6792%
17 | Kheda-Nadiad | 411.1559 | 400.7216 | -4.3384 | -1.055%
18 | Kutch-Bhuj | 485.4717 | 468.9041 | -9.4206 | -1.94%
19 | Mahisagar | 280.7802 | 278.7712 | 2.5201 | 0.8975%
20 | Mehsana | 353.3635 | 340.3366 | -7.5243 | -2.129%
21 | Morbi | 138.0325 | 134.3833 | -1.4967 | -1.084%
22 | Narmda | 179.945 | 176.33 | -1.222 | -0.6791%
23 | Navsari | 85.6916 | 85.5863 | 1.2331 | 1.439%
24 | Panchmahals | 460.8415 | 443.5114 | -17.6133 | -3.822%
25 | Patan | 253.8785 | 245.2267 | -5.6326 | -2.219%
26 | Porbandar | 76.8935 | 75.0036 | -0.61237 | -0.7964%
27 | Rajkot | 297.7442 | 293.1048 | 0.073517 | 0.02469%
28 | Sabarkantha | 413.4498 | 403.0768 | -3.7398 | -0.9045%
29 | Surat | 409.8797 | 394.2696 | -10.9734 | -2.677%
30 | Surendranagar | 352.1304 | 335.7381 | -8.1612 | -2.318%
31 | Tapi | 233.2444 | 224.7008 | -4.9259 | -2.112%
32 | Vadodara | 289.1512 | 283.4941 | -1.2242 | -0.4234%
33 | Valsad | 223.244 | 213.3811 | -6.3933 | -2.864%
| TOTAL | 9632.9 | 9364.04 | -135.9079 | -1.411%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Reconciliation of MME OB, Allocation & Releasing [PY + U PY]
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 1213.98 | 1213.98 | 0 | 0%
2 | Opening Balance as on 01.04.2019 | 0 | 0 | 0 | 0%
3 | Released during 2019-20. | 1213.98 | 1213.98 | 0 | 0%
4 | Total Availibility | 1213.98 | 1213.98 | 0 | 0%
7.2) Utilisation of MME during 2019-20 (Source data: Table AT-10 of AWP&B 2020-21)
|  |  |  | (Rs. In lakh) | (As on 31.03.2020)
Sl. No. | Activity | Allocated | Total Availibility | Expenditure | Exp as % of allocation
1 | 2 | 3 | 4 | 5 | 6
1 | School Level Expenses | 606.99 | 606.99 | 547.55 | 90.21%
2 | Management, Supervision, Training & Internal Monitoring, External Monitoring & Evaluation | 606.99 | 606.99 | 355.844 | 58.62%
Total |  | 1213.98 | 1213.98 | 908.394 | 74.83%
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Reconciliation of TA OB, Allocation & Releasing [PY + U PY]
Sl. No. | Activity | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Allocation for 2019-20 | 1728.8 | 1728.8 | 0 | 0%
2 | Opening Balance as on 01.04.2019 | 61.73 | 61.73 | 0 | 0%
3 | Released during 2019-20. | 1667.07 | 1667.07 | 0 | 0%
4 | Total Availibility | 1728.8 | 1728.8 | 0 | 0%
8.2) Utilisation of TA during 2019-20 (Source data: Table AT-9 of AWP&B 2020-21)
(Rs. In lakh)
Allocated for 2019-20 | Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissibale | actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6=(4-5) | 7 | 8= (2-5)
1728.8 | 1728.8 | 116965.318 | 1754.4798 | 877.24 | 877.2398 | 50.74% | 851.56
9. INFRASTRUCTURE DEVELOPMENT DURING 2019-20 (Primary + Upper primary)
Kitchen-cum-Stores
9.1) Releasing details
9.1.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.3.2020
Schools | Installment | Dated | Units | Amount (Rs in lakh)
Primary + Upper-Primary | 2006-07 |  | 6318 | 3790.56
| 2008-09 |  | 9303 | 5581.8
| 2009-10 |  | 4247 | 4415.07
| 2013-14 |  | 5209 | 9415.72
| Sub total |  | 25077 | 23203.15
9.2) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-2019 | 25077 | 23203.15 | 25077 | 23203.15 | 0% | 0%
9.3) Achievement ( under MDM Funds) (Source data: Table AT-10 of AWP&B 2020-21)
Sanctioned by GoI during 2006-07 to 2019-20 |  | Cosntructed upto 31.03.2020 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
25077 | 23203.15 | 24310 | 23203.15 | 96.94% | 100%
10. Kitchen Devices
10.1) Reconciliation of amount sanctioned
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin |  |  |  | 1677
2006-18 | 33540 | 1677 | 33540 | 1677 | 0% | 0% |  |  |  | 1493.4
2012-13 to 2019-20 (Replacement) | 29868 | 1493.4 | 29868 | 1493.4 | 0% | 0%
10.2) Achievement ( under MDM Funds) (Source data: Table AT-11 of AWP&B 2020-21)
| Sanctioned during 2006-07 to 2019-20 |  | Achievement (Procured+IP) |  | Achievement as % of allocation
| Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7
2006-10 | 33540 | 1677 | 33540 | 1677 | 0% | 0%
2012-13 -2019-20 (Replacement) | 29868 | 1493.4 | 29868 | 1493.4 | 0% | 0%
Benchmark (85%)
100%
68%