## Slide 1: PAB - MDM Meeting for Review of Implementation of MDMS in Jharkhand on 29-04-2020
Mid Day Meal Scheme

## Slide 2: Best Practices
Ministry of HRD, Govt. of India
i) Conducted Social Audit in 4856 schools in all 24 districts through Social Audit Unit Jharkhand during 2019-20.
Additional contribution of Rs. 500/-pm to honorarium of cook-cum-helpers from State’s own resources.
Distribution of 200 ml Milk per child per day in convergences with NDDB (National Dairy Development Board) in 4 districts viz. Ranchi (17 schools), Bokaro (7 Schools), Latehar (36 schools) and Hazaribagh(7 Schools) covering one lakh children.
One Egg per child twice a week (Monday and Friday) has been provided through State’s own resources.

## Slide 3: Best Practices
Ministry of HRD, Govt. of India
v) Provision of additional Rs. 276.40 Lakh under MME from State’s own resources for strengthening district and block MDM Cell.
Active participation by Bal Sansad in each school during serving of MDM.

## Slide 4: Issues
Ministry of HRD, Govt. of India
Less coverage of the children against the enrolment both in primary (66%) and upper primary (63%).
Slow progress in construction of kitchen-cum-stores against sanctioned during 2009-10 and 2011-12.
Less coverage under Health components specially distribution of Iron and Folic Acid and De-worming tablets.

## Slide 5: Coverage of Children (Primary & U. Primary)
Chart: 
| Jharkhand
%age Coverage (Pry) | 0.8
%age Coverage U.Pry | 0.88
Children (Primary) |  |  |  | Children (Upper Primary) |  | 
State | PAB Approval | Coverage | %age | PAB Approval | Coverage | %age
Jharkhand | 2298182 | 1841662 | 80% | 997048 | 872861 | 88%
Ministry of HRD, Govt. of India

## Slide 6: Working Days (Primary & U. Primary)
Chart: 
| Jharkhand
%age Coverage (Pry) | 0.96739
%age Coverage U.Pry | 0.96739
Ministry of HRD, Govt. of India
State | Working Days (Pry) |  |  | Working Days (U.Pry) |  | 
 | PAB Approval | Coverage | % | PAB Approval | Coverage | %
Jharkhand | 184 | 178 | 97 | 184 | 178 | 97

## Slide 7
Engagement of Cook-cum-Helpers (Primary & U. Primary)
State | PAB Approval | Coverage | %age
Jharkhand | 79591 | 79,591 | 100%
Chart: % Coverage of CCH against PAB approval
| Jharkhand
%age Coverage (Pry) | 1
Ministry of HRD, Govt. of India

## Slide 8
Procurement of Kitchen Devices (Primary & U. Primary)
Kitchen Devices | Sanctioned | Procured | %age
New Kitchen Devices | 37132 | *37124 | 99.98%
Replacement of Kitchen devices | 15849 | 15849 | 100%
Chart: % Procurement of Kitchen Devices against sanctioned
| New Kitchen Devices | Replacement of Kitchen devices
%age Coverage | 0.9998 | 1
Ministry of HRD, Govt. of India
* 8 Kitchen devices not procured sanctioned during 2009-10

## Slide 9
Construction of Kitchen-cum-Stores (Primary & U. Primary)
Chart: % Construction of Kitchen-cum-Store against Sanctioned
| Jharkhand
% Construction of Kitchen-cum-Store against Sanctioned | 0.83
State | Sanctioned | Constructed | %age
Jharkhand | 39001 | 32523 | 83%
Ministry of HRD, Govt. of India

## Slide 10
Setting up of School Nutrition Gardens (SNG)
No. of Schools | No. of schools having SNG | %
35773 | 2991 | 8%
Ministry of HRD, Govt. of India
Chart: School Nutrition Garden
| % schools having School Nutrition Gardens
Series 1 | 0.083611

## Slide 11: Health Component - Performance
Ministry of HRD, Govt. of India
Details | Institutions | Children
Total in State | 35773 | 4180954
Health check up | 32617 | 3458088
IFA Distribution | 24715 | 1897336
Deworming Tablets | 25566 | 2633484
Chart: Coverage of Children
Health check up | 0.82711
IFA Distribution | 0.4538
Deworming Tablets | 0.62988

## Slide 12
MHRD issued guidelines to ensure quality, safety and hygiene under MDMS in 2015
  Testing of meals by NABL accredited laboratories.
  Mandatory tasting of the meal by 2-3 adults including at least one teacher.
MDM Rules 2015 mandates collection of samples once a month from randomly selected schools or centralized kitchens for testing.
Testing may also be done through FSSAI accredited laboratories.
No. of samples |  | Result (No. of samples) | 
Collected | Tested | Meeting norms | Below norms
210 | 210 | 38 | 22
Testing of food samples
Only 60 reports have been received.
150 Reports are still awaited.

## Slide 13
Status of implementation of MIS & AMS
Chart: 
| Annual | Monthly | AMS
% Schools data entered | 0.99911 | 0.9728 | 0.69

## Slide 14: Performance Grading Index (PGI)
Score (children taking MDM) | Score (MDM served days)
8 | 10
Performance Grading Index (PGI):
Score against the weightage of 10 for indicator No. 1.3.7 i.e. “% of elementary school’s children taking MDM against target approved in PAB – in Govt. and aided schools”.
Score against the weightage of 10 for indicator No 1.3.8 i.e. “% of days Mid Day Meal served against total working days – Govt. and aided elementary schools.”
Ministry of HRD, Govt. of India

## Slide 15: Performance Score Card
Ministry of HRD, Govt. of India
Component | PAB-Approval | Achievement | % Achievement
Institutions | 35773 | 35773 | 100%
Children | 3295230 | 2714523 | 82%
Working Days | 184 | 178 | 97%
Food Grain Utilizations (in MTs) | 69862.36 | 56125 | 80%
Cooking Cost (Rs. in Lacs) | 31279.9 | 25128.41 | 80%
CCH Engaged | 79591 | 79591 | 100%
CCH Honorarium (Rs. in Lacs) | 11938.65 | 9550.92 | 80%
TA (Rs. in Lacs) | 820.88 | 646.771 | 79%
MME (Rs. in Lacs) | 937.70 | 877.81 | 94%
Kitchen cum Stores | 39001 | 32523 | 83%
Kitchen Devices | 37132 | 37124 | 100%
Health Check up of children | 4180954 | 3458088 | 83%
Annual Data Entry | 35773 | 35741 | 100%
Monthly Data Entry | 35773 | 34800 | 97%
Chart: 
| Institutions | Children | Working Days | Food Grain | Cooking Cost | CCH Engaged | CCH Honorarium | TA | MME | Kitchen cum Stores | Kitchen Devices | Health Check up | Annual DE | Monthly DE
% Achievement | 10 | 8.2377 | 9.6739 | 8.0337 | 8.0334 | 10 | 8 | 7.879 | 9.3613 | 8.339 | 9.9978 | 8.2711 | 9.9911 | 9.728

## Slide 16: Social Audit
Social Audit is collective monitoring of a scheme by people’s active involvement.
It covers the issues of equity and equality along with expenditure in programme implementation.
The Social Audit Units (SAU) under MNREGS, may be actively involved in conducting Social Audit of MDM in all districts.
Key Features and Benefits:
  It informs and educates people about their rights and entitlements.
  It provides a collective platform for people to ask queries, express their needs and grievances.
  It promotes people's participation in all stages of implementation of programme.
  It brings about transparency and accountability in Govt. schemes.
  It strengthens decentralised governance.
  State has conducted Social Audit in all 24 districts.

## Slide 17: Proposals and Recommendations
S. N | Component | PAB Approval 2019-20 | State’s Proposal for 2020-21 | Recommendations 2020-21
1 | Children (Pry) | 2294782 | 2294717 | 1894264
2 | Children (U Pry) | 997048 | 997048 | 891317
3 | Children (NCLP) | 3400 | 3465 | 3465
4 | Working Days – Pry & Upy | 254 | 253 | 253
5 | Working Days - NCLP | 312 | 310 | 310
6 | Cook-cum-Helpers (Pry +U.Pry) | 79591 | 79591 | 79591
7 | MDM during Drought |  |  | 
7.1 | Children (Pry) | 1701348 | Nil | Nil
7.2 | Children (U Pry) | 744254 | Nil | Nil
7.3 | Working Days | 25 | Nil | Nil
7.4 | Cook-cum-Helpers | 60496 | Nil | Nil
8 | Kitchen cum Store | Nil | Nil | Nil
9 | Kitchen cum Stores (Repair) | 12114 | 12114 | 12114
10 | Kitchen Devices (New) | Nil | Nil | Nil
11 | Kitchen Devices (Rep.) | 30497 | 30497 | 30497
Central Assistance (Rs in Lakh) |  | 42272.73 | 39159.20 | 37097.86

## Slide 18: Recommendations of Central Assistance
PAB Approval for FY 2019-20 | State’s Proposal for FY 2020-21 | Recommendations for FY - 2020-21
42272.73 | 39159.20 | 37097.86
(Rs. in Lakhs)
Ministry of HRD, Govt. of India

## Slide 19
Every Meal to a Child is an offering to the Divinity.
Thank You