## FS (2)
Government of India
National Programme of Mid-Day Meal in Schools
Annual Work Plan & Budget 2020-21
Ladakh
Part-D: ANALYSIS SHEET
REVIEW OF IMPLEMENTATION OF MDM SCHEME DURING 2020-21 (01.04.2019 to 31.12.2019)
I. Analysis of Children, Working Days and Meals
Stage | No. of children | [12 empty] | 620
| PAB-MDM Approval for 2019-20 | Average number of children availed MDM during 01.04.2019 to 31.12.2019 (AT-5&5A) | Diff | Diff in % | [10 empty] | 370
Primary | 8769 | 11693 | -2924 | -33.34%
Upp. Primary | 3779 | 4856 | -1077 | -28.5% | [10 empty] | 185
NCLP | 0 | 0 | 0 | 0%
Total | 12548 | 16549 | 4001 | 31.89%
1.2 No. of Working Days Approved for FY 2019-20
S.no | Stage | No of working days approved for FY 2019-20 | [12 empty] | 420
1 | Primary | 220 | [13 empty] | 210
2 | Upper Primary | 220
3 | NCLP | 0
1.1.1) No. of School working days
Stage | MDM PAB Approval for 2019-20 (APR-MAR) | Actuals as per AWP&B 2019-20 (AT-5 &5A) | Diff | Diff in %
Primary | 220 | 187 | -33 | -15%
Upp. Primary | 220 | 187 | -33 | -15%
Average | 220 | 187 | -33 | -15%
NCLP | 0 | 0 | 0 | 0%
1.1.2) No. of Meals (Primary & Upper Primary )
Base period 01.04.2019 to 31.12.2019
Stage | No. of Meals as per PAB approval | Total no. of Meals claimed to have served (Q1+Q2+Q3) | Diff. | Diff in %
Primary | 1929180 | 2186591 | 257411 | 13.34%
Upr. Primary | 831380 | 908072 | 76692 | 9.225%
NCLP | 0 | 0 | 0 | 0%
Total | 2760560 | 3094663 | 334103 | 12.1%
ii) Base period 01.04.2019 to 31.12.2019 (As per PAB aaproval = 220 days for Py & 220 days for U Py)
Stage | No. of Meals as per PAB approval (01.04.2019 to 31.12.2019) | No. of Meals served by State during the period 01.04.2019 to 31.12.2019 |  | Bench Mark as per State's claim
Py | 1929180 | 2186591 |  | 113.3%
Upr. Py | 831380 | 908072 |  | 109.2%
NCLP | 0 | 0 |  | 0%
Total | 2760560 | 3094663 |  | 112.1%
2. COVERAGE UNDER MDM
2.1 Institutions- (Primary( (Class I-V only) *(Source data : Table AT-3A of AWP&B 2020-21)
Sl. No. | Districts | No. of Existing Institutions | No. of Institutions serving MDM | Non-Coverage | % NC
1 | Kargil | 239 | 215 | 24 | 10.04%
2 | Leh | 198 | 138 | 60 | 30.3%
| Total | 437 | 353 | 84 | 19.22%
2.2 Institutions- (Upper Primary + Upper Primary with Primary) (Class - V-VIII + I-VIII) *(Source data : Table AT-3B & 3C of AWP&B 2020-21) | [7 empty] | Existing |  |  |  | Serving
Sl. No. | Districts | No. of Existing Institutions | No. of Institutions serving MDM | Non-Coverage | % NC |  |  | With Primary | Without Primary | Total |  | With Primary | Without Primary | Total
1 | Kargil | 310 | 308 | 2 | 0.6452% |  |  | 280 | 30 | 310 |  | 278 | 30 | 308
2 | Leh | 160 | 156 | 4 | 2.5% |  |  | 155 | 5 | 160 |  | 151 | 5 | 156
| Total | 470 | 464 | 6 | 1.277% |  |  | 435 | 35 | 470 |  | 429 | 35 | 464
Type of Institute
2.1 Institutions- (Primary) *(Source data : Table AT-3A of AWP&B 2020-21)
Sl. No. | Type of Institute | Existing Institute | No. of Institutions serving MDM | Non-Coverage | % NC
1 | (Govt+LB) | 437 | 353 | 0 | 0%
2 | GA | 0 | 0 | 0 | 0%
3 | EGS / AIE Centres | 0 | 0 | 0 | 0%
4 | Madarsas/ Maqtab | 0 | 0 | 0 | 0%
5 | NCLP | 0 | 0 | 0 | 0%
| Total | 437 | 353 | 84 | 19.22%
2.2 Institutions- (Upper Primary) *(Source data : Table AT-3B & 3C of AWP&B 2020-21)
Sl. No. | Type of Institute | Existing Institute | No. of Institutions serving MDM | Non-Coverage | % NC
1 | (Govt+LB) | 470 | 464 | 6 | 1.277%
2 | GA | 0 | 0 | 0 | 0%
3 | EGS / AIE Centres | 0 | 0 | 0 | 0%
4 | Madarsas/ Maqtab | 0 | 0 | 0 | 0%
5 | NCLP | 0 | 0 | 0 | 0%
| Total | 470 | 464 | 6 | 1.277%
2.3 No. of children ( Primary) *(Source data : Table AT-5 of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availed MDM | Diff | % Diff |  | Districts | Pry/No. of children as per PAB Approval for 2014-15 | PAB NCLP | TOTAL PAB | Pry/Average number of children availing MDM | AVERAGE NO OF CHILDREN NCLP | AVERAGE TOTAL
1 | Kargil | 4948 | 8523 | 3575 | 72.25% |  | Jammu |  |  | 0 |  |  | 0
2 | Leh | 3821 | 3170 | -651 | -17.04% |  | Samba |  |  | 0 |  |  | 0
| Total | 8769 | 11693 | 2924 | 33.34% |  | Total | 0 | 0 | 0 | 0 | 0 | 0
2.4 No. of children ( Upper Primary) *(Source data : Table AT-5A of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availed MDM | Diff | % Diff |  | Districts | No. of children as per PAB Approval for 2019-20 | Average number of children availing MDM | Diff | % Diff | [6 empty] | total
1 | Kargil | 2486 | 3552 | 1066 | 42.88% |  | Anantnag |  |  | 0 | #DIV/0! | [6 empty] | 0
2 | Leh | 1293 | 1304 | 11 | 0.8507% |  | Shopian |  |  | 0 | #DIV/0! | [6 empty] | 0
| Total | 3779 | 4856 | 1077 | 28.5% |  | Total | 0 | 0 | 0 | #DIV/0! |  |  |  |  | 0 | 0 | 0
2.5 No. of children ( Primary) *(Source data : Table AT-4 of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per Enrolment for 2019-20 | Average number of children availed MDM | Diff | % Diff | [10 empty] | No. of children as per Enrolment for 2014-15 |  |  | Average number of children availing MDM
1 | Kargil | 8523 | 8523 | 0 | 0% | [8 empty] | 15955 | 170 | 16125 | 11718 | 157 | 11875
2 | Leh | 3182 | 3170 | -12 | -0.3771%
| Total | 11705 | 11693 | -12 | -0.1025%
2.6 No. of children ( Upper Primary) *(Source data : Table AT-4A of AWP&B 2020-21)
Sl. No. | Districts | No. of children as per Enrolment for 2019-20 | Average number of children availed MDM | Diff | % Diff
1 | Kargil | 3552 | 3552 | 0 | 0%
2 | Leh | 1320 | 1304 | -16 | -1.212%
| Total | 4872 | 4856 | -16 | -0.3284%
2.7 No. of meals to be served & actual no. of meals served during 2019-20 [PRIMARY]
*(Refer col.6 of table AT- 5 & 5B, AWP&B, 2020-21)
Sr. No. | District | No of meals to be served during 01.04.2019 to 31.12.2019 | No of meal served during 2019-20 | % Meals served |  |  |  | Pry/No. of MEALS as per PAB Approval for 2019-20 | PAB NCLP | TOTAL PAB | Pry/Average MEALS Served | AVERAGE NO OF Meals NCLP | AVERAGE TOTAL
1 | Kargil | 1088560 | 1593801 | 146.4% | [5 empty] | 0 |  |  | 0
2 | Leh | 840620 | 592790 | 70.52% | [5 empty] | 0 |  |  | 0
| Total | 1929180 | 2186591 | 113.3% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.8 No. of meals to be served & actual no. of meals served during 2019-20 [UPPER PRIMARY]
*(Refer col. 6 of table AT- 5A , AWP&B, 2020-21)
Sl. No. | District | No of meals to be served during 01.04.2019 to 31.12.2019 | No of meal served during 2019-20 | % Meals served
1 | Kargil | 546920 | 664224 | 121.4%
2 | Leh | 284460 | 243848 | 85.72%
| Total | 831380 | 908072 | 109.2%
3. ANALYSIS OF FOOD GRAINS (PRIMARY+UPPER PRIMARY)
3.1) Reconciliation of Foodgrains OB, Allocation & Lifting
Sl. No. | Particulars | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Stock as on 01.04.2019 | 0 | 0 | 0 | 0%
2 | Allocation for 2019-20 | 435.19 | 435.19 | 0 | 0%
3 | Lifting as on 31.12.2019 | 245.6 | 245.6 | 0 | 0%
3.2) ANALYSIS ON OPENING STOCK AND UNSPENT STOCK OF FOODGRAINS
District-wise opening balance as on 01.04.2019
*(Refer col. 4 and 9 of table AT- 6 and AT-6A, AWP&B, 2020-21)
S.No. | Name of District | Allocation for 2019-20 | Opening Stock as on 01.04.2019 | % of OS on allocation 2019-20 |  |  | ALLOCATION PRY | ALLOCATION UPR PRY | ALLOCATION TOTAL |  | OPENING BALANCE PRY | OPENING BALANCE UPR PRY | OPENING BALANCE TOTAL
1 | Kargil | 304.7 | 0 | 0% |  |  | 187.5 | 117.2 | 304.7 |  | 0 | 0 | 0
2 | Leh | 130.49 | 0 | 0% |  |  | 80.54 | 49.95 | 130.49 |  | 0 | 0 | 0
| Total | 435.19 | 0 | 0% |  |  | 268.04 | 167.15 | 435.19 |  | 0 | 0 | 0
3.3) District-wise unspent balance as on 31.12.2019
(Refer col. 7 and 12 of table AT- 6 and AT-6A, AWP&B, 2020-21) |  |  |  | (in MTs) | [20 empty] | QQQQQQQQQQQQQQQQQ1``q
Sl. No. | Name of District | Allocation for 2019-20 | Unspent Balance as on 31.12.2019 | % of UB on allocation 2019-20 |  |  | LIFTED PRY | LIFTED UPR PRY | LIFTED TOTAL |  | CONSUMED PRY | CONSUMED UPR PRY | CONSUMED TOTAL |  | CLOSING BALANCE PRY | CLOSING BALANCE UPR PRY | UNSPENT BALANCE TOTAL
1 | Kargil | 304.7 | -128.02 | -42.02% |  |  | 75.56 | 55.43 | 130.99 |  | 159.38 | 99.63 | 259.01 |  | -83.82 | -44.2 | -128.02
2 | Leh | 130.49 | 18.75 | 14.37% |  |  | 68.35 | 46.26 | 114.61 |  | 59.28 | 36.58 | 95.86 |  | 9.07 | 9.68 | 18.75
| Total | 435.19 | -109.27 | -25.11% |  |  | 143.91 | 101.69 | 245.6 |  | 218.66 | 136.21 | 354.87 |  | -74.75 | -34.52 | -109.27
3.4) Foodgrains Allocation & Lifting
(in MTs)
Allocation | OB as on 01.04.2019 | Lifting upto 31.12.2019* | Total availibility | % availibility | Bench mark (85%)
435.19 | 0 | 245.6 | 245.6 | 56.44% | 369.9115
* Lifting reported by UT
3.5) District-wise Foodgrains availability as on 31.12.2019
*(Refer col. 5 of table AT- 6 and AT-6A, AWP&B, 2020-21)
Sl. No. | District | Allocation for 2019-20 | OB as on 01.04.2019 | Lifted | Total Availibility | % Availibility
1 | Kargil | 304.7 | 0 | 130.99 | 130.99 | 42.99%
2 | Leh | 130.49 | 0 | 114.61 | 114.61 | 87.83%
| Total | 435.19 | 0 | 245.6 | 245.6 | 56.44% | [11 empty] | #REF!
3.6) Foodgrains Allocation, Lifting (availibility) & Utilisation
Allocation | Availability | % availability | Utilisation | % Utilisation
435.19 | 245.6 | 56.44% | 354.87 | 81.54%
3.7) District-wise Utilisation of foodgrains
*(Refer col. 6 of table AT- 6 and AT-6A, AWP&B, 2020-21)
Sl. No. | District | Allocation for 2019-20 | Utilisation | % Utilisation
1 | Kargil | 304.7 | 259.01 | 85%
2 | Leh | 130.49 | 95.86 | 73.46%
| Total | 435.19 | 354.87 | 81.54%
3.8) ANALYSIS ON COST OF FOOD GRAINS [PRIMARY + UPPER PRIMARY]
3.8.1) Releasing details
Releases for Cooking cost by GoI (2019-20)
Stage | Installment | Dated | Amount (Rs. In lakh)
Primary +Upper primary | OB as on 01.04.2019 | 01.04.2019 | 0.84
| Adhoc Released | 25.04.2019 | 2.53
| Balance of 1st Installment / Revalidation | 30.03.2020 | 5.31
| 2nd Installment | -- | --
| Grand total |  | 8.68
3.8.2) Cost of Foodgrains : Allocation, Releases (availability) & Utilisation
Allocation | Availability | % Availability | Bills submited by FCI | Payment made to FCI | % payment
13.05 | 8.68 | 66.51% | 7.37 | 0 | 0% | [9 empty] | 675.77
[15 empty] | #REF! | 1.62 | #REF!
3.9) Payment of Cost of foodgrains to FCI | [5 empty] | (Rs. in Lakhs)
S.No. | Name of District | Allocation | Bills raised by FCI | Payment to FCI by State* | Pending Bills | Bill paid
1 | Kargil | 7.8 | 3.93 | 0 | 3.93 | 0%
2 | Leh | 5.25 | 3.44 | 0 | 3.44 | 0%
| Total | 13.05 | 7.37 | 0 | 7.37 | 0% | DETAIL BREAK-UP REQUIRED FOR PAYMENT
4. ANALYSIS ON COOKING COST [PRIMARY + UPPER PRIMARY]
4.1) Releasing details
Releases for Cooking cost by GoI (2019-20)
Stage | Installment | Dated | Amount (Rs. In lakh)
Primary +Upper primary | OB as on 01.04.2019 | 01.04.2019 | 0 |  |  |  |  | 1338.41
| Adhoc Released | 25.04.2019 | 32.92 |  |  |  |  | 2.76 | 1341.17
| Balance of 1st Installment / Revalidation | 30.03.2020 | 75.65 |  |  |  |  | 1355.98
| 2nd Installment | -- | -- |  |  |  |  | 6.92 | 1362.9
| Grand total |  | 108.57 |  |  |  |  | 3275.57
4.2) ANALYSIS ON OPENING BALANCE AND CLOSING BALANCE
4.2.1) District-wise opening balance as on 01.04.2019
*(Refer col. 8 of table AT- 7 and AT-7A, AWP&B, 2020-21) |  |  |  | (Rs. in Lakhs)
S.No. | Name of District | Allocation for 2019-20 | Opening Balance as on 01.04.2019 | % of OB on allocation 2019-20 |  |  |  | ALLOCATION PRY | ALLOCATION U PRY | TOTAL ALLOCATION |  | OPENING BALANCE PRY | OPENING BALALNCE UPR PRY | TOTAL OPENING BALANCE |  | RELEASE PRY | RELEASE UPR PRY | TOTAL RELEASE
1 | Kargil | 124.94 | 0 | 0% |  |  |  | 72.24 | 52.7 | 124.94 |  | 0 | 0 | 0 |  | 55.76 | 23.41 | 79.17
2 | Leh | 69.9 | 0 | 0% |  |  |  | 47.75 | 22.15 | 69.9 |  | 0 | 0 | 0 |  | 20.73 | 8.67 | 29.4
| Total | 194.84 | 0 | 0% |  |  |  | 119.99 | 74.85 | 194.84 |  | 0 | 0 | 0 |  | 76.49 | 32.08 | 108.57
4.2.2) District-wise unspent balance as on 31.12.2019
*(Refer col. 17 of table AT- 7 and AT-7A, AWP&B, 2020-21) |  |  |  | (Rs. in Lakhs)
S.No. | Name of District | Allocation for 2019-20 | Unspent Balance as on 31.12.2019* | % of UB on allocation 2019-20 |  |  |  | Expenditure PRY | Expenditure UPR PRY | TOTAL Expenditure |  | Unspent Pry. | Unspenr U. Pry. | TOTAL RELEASE
1 | Kargil | 124.94 | -36.8 | -29.45% |  |  |  | 71.4 | 44.57 | 115.97 |  | -15.64 | -21.16 | -36.8
2 | Leh | 69.9 | -13.53 | -19.36% |  |  |  | 26.56 | 16.37 | 42.93 |  | -5.83 | -7.7 | -13.53
| Total | 194.84 | -50.33 | -25.83% |  |  |  | 97.96 | 60.94 | 158.9 |  | -21.47 | -28.86 | -50.33
4.3) Cooking cost allocation and disbursed to Districts
Allocation | OB as on 01.04.2019 | Disbursed to Dist | Total Availibility | % Availibility | Bench mark (85%)
194.84 | 0 | 108.57 | 108.57 | 55.72% | 165.614
4.4) District-wise Cooking Cost availability
*(Refer col.11 of table AT- 7 and AT-7A, AWP&B, 2020-21) | [5 empty] | (Rs. in Lakhs)
S.No. | Name of District | Allocation for 2019-20 | Opening Balance as on 01.04.2019* | Cooking assistance received* | Total Availibility of cooking cost as on 31.12.2019 | % Availibility of cooking cost
1 | Kargil | 124.94 | 0 | 79.17 | 79.17 | 63.37%
2 | Leh | 69.9 | 0 | 29.4 | 29.4 | 42.06%
| Total | 194.84 | 0 | 108.57 | 108.57 | 55.72%
4.5) Cooking Cost Utilisation
Allocation | Availability | % Availability | Utilisation | % Utilisation
194.84 | 108.57 | 55.72% | 158.9 | 81.55%
4.6) District-wise Utilisation of Cooking cost
*(Refer col. 14 of table AT- 7 and AT-7A, AWP&B, 2020-21) |  |  |  | (Rs. in Lakhs)
S.No. | Name of District | Allocation for 2019-20 | Utilisation of Cooking assistance* | % Utilisation | [9 empty] | Name of District | UTILISATON PRY | UTILISATION UPR PRY | TOTAL UTILISATON
1 | Kargil | 124.94 | 115.97 | 92.82% | [12 empty] | 0
2 | Leh | 69.9 | 42.93 | 61.42% | [12 empty] | 0
| Total | 194.84 | 158.9 | 81.55% | [9 empty] | TOTAL | 0 | 0 | 0
5. Reconciliation of Utilisation and Performance during 2019-20 [PRIMARY+ UPPER PRIMARY]
5.1 Mismatch between Utilisation of Foodgrains and Cooking Cost (Source data: para 3.8 and 4.7 above)
Sr. No. | District | % utilisation of foodgrains | % utilisation of Cooking cost | Mis-match in % points
1 | Kargil | 85% | 92.82% | 7.8156
2 | Leh | 73.46% | 61.42% | -12.0453
Total |  | 81.54% | 81.55% | 0.010402
5.2 Reconciliation of Food grains utilisation during 2019-20 (Source data: para 2.5 and 3.7 above)
(In MTs)
Sr. No. | District | No. of Meals served during 01.4.18 to 31.12.2019 | Expected consumption of food grains | Actual consumption of food grains | % Utilisation |  |  |  | District | No. of Meals served ( Pry ) | No. of Meals served during Upr Pry | Total | Actual Utilisation |  | District | No of Meals Pry | Formulae for Pry | No. of Meals Upr Pry | Formulae for Upr Pry | Expected Consumption of food grains | District | Actual Consumptin of Food Grains Pry | Actual Consumptin of Food Grains Upr Pry | Total Consumption of Food Grains
1 | Kargil | 2258025 | 259.0137 | 259.01 | 100% |  |  |  | Kargil | 1593801 | 664224 | 2258025 |  |  | Kargil | 1593801 | 159.3801 | 664224 | 99.6336 | 259.0137 | Jammu |  |  | 0
2 | Leh | 836638 | 95.8562 | 95.86 | 100% |  |  |  | Leh | 592790 | 243848 | 836638 |  |  | Leh | 592790 | 59.279 | 243848 | 36.5772 | 95.8562 | Samba |  |  | 0
Total |  | 3094663 | 354.8699 | 354.87 | 100% |  |  |  | Total | 2186591 | 908072 | 3094663 | 0 |  | Total | 2186591 | 218.6591 | 908072 | 136.2108 | 354.8699 | Total | 0 | 0 | 0
5.3) Reconciliation of Cooking Cost utilisation during 2019-20 (Source data: para 2.5 and 3.7 above)
(Rs. in Lakhs)
Sr. No. | District | No. of Meals served during 01.4.18 to 31.12.2019 | Expected Utilisation of Cooking Cost (Rs. In Lakhs) | Actual utilisation of Cooking cost (Rs. In Lakhs) | % Utilisation |  |  |  | Districts | No. of Meals served ( Pry ) | Expected Utilisation of Cooking Cost / Pry | No. of Meals served during Upr Pry | Expected Utilisation of Cooking Cost Upr Pry | GR. TOTAL EXPECTED CC |  | District | Actual utilisation of Cooking cost (Pry) | Actual utilisation of Cooking cost (Upr Pry) | Total Utilisation of Cooking Cost
1 | Kargil | 2258025 | 115.9717 | 115.97 | 100% |  |  |  | Kargil | 1593801 | 71.4023 | 664224 | 44.5694 | 115.9717 |  | Kargil | 71.4 | 44.57 | 115.97
2 | Leh | 836638 | 42.9192 | 42.93 | 100% |  |  |  | Leh | 592790 | 26.557 | 243848 | 16.3622 | 42.9192 |  | Leh | 26.56 | 16.37 | 42.93
Total |  | 3094663 | 158.8909 | 158.9 | 100% |  |  |  | Total | 2186591 | 97.9593 | 908072 | 60.9316 | 158.8909 |  | Total | 97.96 | 60.94 | 158.9
6. ANALYSIS of HONORIUM, To COOK-CUM-HELPERS
4.1) Releasing details
Releases for Cooking cost by GoI (2019-20)
Stage | Installment | Dated | Amount (Rs. In lakh)
Primary +Upper primary | OB as on 01.04.2019 | 01.04.2019 | -5.65
| Adhoc Released | 25.04.2019 | 14.86
| Balance of 1st Installment / Revalidation | 30.03.2020 | 34.43
| 2nd Installment | -- | --
| Grand total |  | 43.64
6.1) District-wise allocation and availability of funds for honorium to cook-cum-Helpers
S.No. | Name of District | Allocation for 2019-20 | Opening Balance as on 01.04.2019 | Amount released | Total availability | % Availibility |  | Allocation Pry | Allocation Upr Pry | Total |  | Opening Balance Pry | Opening Balance Upr Pry | Total |  | Amount Release Pry | Amount Release Upr Pry | Total Amount Released
1 | Kargil | 58.03 | 0 | 31.36 | 31.36 | 54.04% |  | 23.9 | 34.13 | 58.03 |  | 0 | 0 | 0 |  | 12.92 | 18.44 | 31.36
2 | Leh | 32.87 | -5.65 | 17.93 | 12.28 | 37.36% |  | 14.65 | 18.22 | 32.87 |  | -2.63 | -3.02 | -5.65 |  | 7.38 | 10.55 | 17.93
| Total | 90.9 | -5.65 | 49.29 | 43.64 | 48.01% |  | 38.55 | 52.35 | 90.9 |  | -2.63 | -3.02 | -5.65 |  | 20.3 | 28.99 | 49.29
6.2) District-wise utilisation Utilisation of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B,2020-21
S.No. | Name of District | Allocation for 2019-20 | Total Availability | Payment of Hon. to CCH | % payment to CCH against allocation |  |  | Payment to CCH Pry | Payment to CCH Upr Pry | Total |  | Unspent Balance Pry | Unspent Balance Upr Pry | Total Unspent Balance
1 | Kargil | 58.03 | 31.36 | 50.04 | 86.23% |  |  | 20.61 | 29.43 | 50.04 |  | -7.69 | -10.99 | -18.68
2 | Leh | 32.87 | 12.28 | 28.62 | 87.07% |  |  | 12.42 | 16.2 | 28.62 |  | -7.67 | -8.67 | -16.34
| Total | 90.9 | 43.64 | 78.66 | 86.53% |  |  | 33.03 | 45.63 | 78.66 |  | -15.36 | -19.66 | -35.02
6.3) District-wise status of unspent balance of grant for Honorarium, cooks-cum-Helpers
Refer table AT_8 and AT-8A,AWP&B,2020-21 |  |  |  |  | (Rs. in Lakhs)
S.No. | Name of District | Allocation for 2019-20 | Total Availability | Unspent balance as on 31.12.2019 | % of UB as on Allocation 2019-20
1 | Kargil | 58.03 | 31.36 | -18.68 | -32.19%
2 | Leh | 32.87 | 12.28 | -16.34 | -49.71%
| Total | 90.9 | 43.64 | -35.02 | -38.53%
7. ANALYSIS ON MANAGEMENT, MONITORING & EVALUATION (MME)
7.1) Releasing details
Releases for Cooking cost by GoI (2019-20)
Stage | Installment | Dated | Amount (Rs. In lakh)
Primary +Upper primary | OB as on 01.04.2019 | 01.04.2019 | 0
| Adhoc Released | 25.04.2019 | 0
| Balance of 1st Installment / Revalidation | 30.03.2020 | 4.57
| 2nd Installment | -- | --
| Grand total (Adhoc + BAL. of 1st) |  | 4.57
7.2) Reconciliation of MME OB, Allocation & Releasing [PY + U PY] *(Refer AT-9, AWP&B, 2020-21)
Sl. No. |  | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Balance as on 01.04.2019 | 0 | 0 | 0 | 0
2 | Allocation for 2019-20 | 7.62 | 7.62 | 0 | 0 | [8 empty] | 103.65 | 83.21 | 0.17 | 187.03
3 | Released during 2019-20 | 4.57 | 4.57 | 0 | 0 | [8 empty] | 45.98 | 54.62 | 0.1 | 100.7
4 | Total Availibility | 4.57 | 4.57 | 0 | 0
7.3) Utilisation of MME during 2019-20 |  |  | (Rs. in Lakhs) | (As on 31.12.2019)
Sl. No. | Activity | Allocation for 2019-20 | Total Availability | Exp. | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | School Level Expenses | 3.25 | 4.57 | 6.13 | 188.6% | -4.13
2 | Management, Supervision, Training , External & Internal Monitoring | 4.37 |  | 5.61 |  | -3.04
Total |  | 7.62 | 4.57 | 11.74 | 154.1% | -7.17
8. ANALYSIS ON CENTRAL ASSISTANCE TOWARDS TRANSPORT ASSISTANCE
8.1) Releasing details
Releases for Cooking cost by GoI (2019-20)
Stage | Installment | Dated | Amount (Rs. In lakh)
Primary +Upper primary | OB as on 01.04.2019 | 01.04.2019 | 0
| Adhoc Released | 25.04.2019 | 1.14
| Balance of 1st Installment / Revalidation | 30.03.2020 | 2.39
| 2nd Installment | -- | --
| Grand total |  | 3.53
* + ** This include NCLP fund
8.2) Reconciliation of TA OB, Allocation & Releasing [PY + U PY] (Refer AT-9, AWP&B, 2020-21)
Sl. No. | Details | As per GoI record | As per State's AWP&B | Diff | % Diff
1 | 2 | 3 | 4 | 5(4-3) | 6
1 | Opening Balance as on 01.04.2019 | 0 | 0 | 0 | 0%
2 | Allocation for 2019-20 | 5.88 | 5.88 | 0 | 0% | [9 empty] | 161.47 | 127.96 | 0.39 | 289.82
3 | Released during 2019-20 | 3.53 | 3.53 | 0 | 0% | [9 empty] | 81.29 | 66.37 | 0.23 | 147.89
4 | Total Availability | 3.53 | 3.53 | 0 | 0%
8.3) Utilisation of TA during 2019-20
Allocated for 2019-20 |  |  | (Rs. in Lakhs) |  | (As on 31.12.2019)
Total availibility of funds | Foodgrains Lifted (in MTs) | Maximum fund permissible* | Actual expenditure incurred by State | Diff | Exp as % of allocation | Unspent Balance
1 | 2 | 3 | 4 | 5=(3-4) | 6 | 7= (1-4)
3.53 | 245.6 | 3.3156 | 3.32 | -0.0044 | 56.46% | 0.21
9. INFRASTRUCTURE DEVELOPMENT DURING 2019-20
9.1) Kitchen cum stores
9.1.1) Releasing details
Releases for Kitchen sheds by GoI as on 31.12.2019
Schools | Year | Dated | Units | Amount (Rs. in Lakhs)
PY& UPY | (2006-07) |  | 0 | 0
| (2007-08) |  | 143 | 55.8
| (2008-09) |  | 87 | 90.18
| (2009-10) |  | 0 | 0
| (2010-11) |  | 0 | 0
| (2011-12) |  | 97 | 77.62
| (2012-13) |  | 0 | 0
| (2013-14) |  | 0 | 0
| (2014-15) |  | 0 | 0
| (2015-16) |  | 0 | 0
| (2016-17) |  | 0 | 0
| (2017-18) |  | 0 | 0
| (2018-19) |  | 0 | 0
| (2019-20) |  | 0 | 0
| Total |  | 327 | 223.6
9.1.2) Reconciliation of amount sanctioned (Refer AT-11, AWP&B, 2020-21)
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-07 to 2019-20 | 327 | 223.6 | 327 | 223.6 | 0% | 0%
9.1.3) Achievement ( under MDM Funds)
Sanctioned by GoI during 2006-17 |  | Achievement (C+IP) upto 31.12.2019 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6
327 | 223.6 | 327 | 223.6 | 100% | 100%
9.2 Kitchen Devices
9.2.1) Releasing details
Releases for Kitchen devices by GoI as on 31.12.2019
|  |  | NEW |  | REPLACEMENT
Schools | Installment | Dated | Units | Amount (Rs. in Lakhs) | Units | Amount (Rs. in Lakhs)
PY & UPY | (2006-07) |  | 781 | 39.05 | 0 | 0
| (2007-08) |  | 0 | 0 | 0 | 0
| (2008-09) |  | 0 | 0 | 0 | 0
| (2009-10) |  | 0 | 0 | 0 | 0
| (2010-11) |  | 0 | 0 | 0 | 0
| (2011-12) |  | 0 | 0 | 0 | 0
| (2012-13) |  | 0 | 0 | 0 | 0
| (2013-14) |  | 0 | 0 | 0 | 0
| (2014-15) |  | 0 | 0 | 0 | 0
| (2015-16) |  | 0 | 0 | 0 | 0
| (2016-17) |  | 0 | 0 | 0 | 0
| (2017-18) |  | 0 | 0 | 0 | 0
| (2018-19) |  | 0 | 0 | 0 | 0
| (2019-20) |  | 0 | 0 | 0 | 0
| Total |  | 781 | 39.05 | 0 | 0
9.2.2) Reconciliation of amount sanctioned (Refer AT-11, AWP&B, 2020-21)
Year | GoI records |  | State record |  | Variation
| Phy | Fin | Phy | Fin | Phy | Fin
2006-07 to 2019-20 | 781 | 39.05 | 781 | 39.05 | 0% | 0%
9.2.3) Achievement ( under MDM Funds)
Sanctioned during 2006-07 to 2019-20 |  | Achievement (C+IP) upto 31.12.2019 |  | Achievement as % of allocation
Phy | Fin (in Lakh) | Phy | Fin (in Lakh) | Phy | Fin
1 | 2 | 3 | 4 |  | 6
781 | 39.05 | 781 | 39.05 | 100% | 100%
Benchmark (85%)
100%
68%

## BASIC-INFOR-FOR-APPRAISAL
S. No. | INDICATORS | STATUS
1. No. of Institutions |  | PRY(I-V) | PY(I-VIII) + U PRY (VI-VIII) | TOTAL
i) | Existing Institutions |  |  | 0
ii) | Covered during the year |  |  | 0
1. No. of Children
[11 empty] | APRIL | 24
i) | Approved by MDM-PAB |  |  | 0 | [6 empty] | MAY | 22
[7 empty] | 615299 | 614 | 615913 |  | JUNE | 26 | 72
Ii) | Enrollment as on 30.9.2014 |  |  | 0 | [6 empty] | JULY | 7
[11 empty] | AUGUST | 25
ii) | Average No. of children availed MDM during 01.04.2014 to 31.12.2014 |  |  | 0 | [6 empty] | SEPTEMBER | 23 | 55
|  | #DIV/0! | #DIV/0! | #DIV/0! | [6 empty] | OCTOBER | 22
2. Coverage of children as per Quarterly Progress Report (QPR) | [10 empty] | NOVEMBER | 23
[11 empty] | DECEMBER | 25 | 70
i) | Average no. of children availed MDM as per QPR-1 |  |  | 0 | [8 empty] | 197
|  | #DIV/0! | #DIV/0! | #DIV/0!
ii) | Average no. of children availed MDM as per QPR-2 |  |  | 0
|  | #DIV/0! | #DIV/0! | #DIV/0!
iii) | Average no. of children availed MDM as per QPR-3 |  |  | 0
|  | #DIV/0! | #DIV/0! | #DIV/0!
3. No. of Working Days | [6 empty] | Q1 | Q2 | Q3 | TOTAL
py
i) | Approved for first 4 quarters |  |  |  |  | WD-APPROV | 72 | 55 | 70 | 197
ii) | Covered during All 4 quarters |  |  |  | PY | WD-COVG. | 54.89 | 57.23 | 52.7 | 164.82
4. |  |  |  |  | UPY |  | 54.61 | 59.24 | 51.58 | 165.43
[5 empty] | TOTAL |  | 54.75 | 58.235 | 52.14 | 165.125
AVERAGE UNIT COOKING COST PCPD |  | 3.72 | 5.56
State’s contributions in cooking cost per child per day |  | 0.41 | 0.62

## release-set-up
2018-19
Sl. No. | Component/ norm | Total | Amount released on ad hoc basis | Unspent Balance | Amount released on balance of 1st installment | Balance amount proposed to be released
|  | Amount admissible |  | as on 01.04.2013
for 2013-2014
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Cost of Food grains (Pry.) (12713.38 MTs x 5650) | 718.3 | 380.67 | 261.01 | 123.32 | 510 |  |  | 0.41 | 0 | 0.6 | 0.68
2 | Cost of Food grains (U. Pry.) (9853.15 MTs x 5650) | 556.7
|  |  | 0.41 | 0 | 0.6 | 0.68
|  |  | 381.08 | 261.01 | 123.92 | 510.68
3 | Cooking cost (Pry.) | 3914.93 | 1654.05 | 2007.38 | 511.4 | 2781.89 | 1.77 | 1655.82 |  | 2.65 | 514.05 | 2.94 | 2784.83
4 | Cooking cost | 3039.79
(U. Pry.)
5 | Honorarium to cook-cum-helper (Pry.) (18080 x ` 750 x 10 months) | 1356 | 556.18 | 524.26 | 456.49 | 1024.62
6 | Honorarium to cook-cum-helper (U. Pry.) (16074 x ` 750 x 10 months) | 1205.55
7 | Transport Assistance | 171.63 | 90.96 | 44.73 | 47.1 | 121.86 | 0.09 | 91.05 |  | 0.15 | 47.25 |  |  | 0.16 | 122.02
(12713.38 MTs x ` 1350)-Primary
8 | Transport Assistance | 133.02
(9853.15 MTs x ` 1350)-U. Pry.
9 | MME @1.8% of the above (Pry.) components | 110.89 | 48.27 | 13.26 | 58.3 | 79.89 | 0.04 | 48.31 |  | 0.06 | 58.36 |  | 0.07 | 79.96
10 | MME @1.8% of the above (Up. Pry.) components | 88.83
| Total | 11295.64 | 2730.13 | 2850.64 | 1196.61 | 4518.26
NCLP
1 | Cost of Food grains (29.99 MTs x 5650) | 1.69 | 0.41 | 0 | 0.6 | 0.68
2 | Cooking cost | 7.36 | 1.77 | 0 | 2.65 | 2.94
3 | Transport Assistance 29.99 MTs x 1350) | 0.4 | 0.09 | 0 | 0.15 | 0.16
4 | MME @1.8% of the above components | 0.17 | 0.04 | 0 | 0.06 | 0.07
| Total | 9.62 | 2.31 | 0 | 3.46 | 3.85
| Grand total | 11305.26 | 2732.44 | 2850.64 | 1200.07 | 4522.11